## Actions
# | Item | Owner | Due | Status
1 | Cable lay sequence – update | Gemma Mitchell | 2026-07-08 | Open
2 | Export cable 2 re-manufacture plan – approval | Ross Davies | 2026-07-26 | Open
3 | Cable lay sequence – review | Eilidh Gray | 2026-08-12 | Done
4 | Export cable 2 re-manufacture plan – approval | Olga Ivanova | 2026-08-24 | In progress
5 | Export cable 2 re-manufacture plan – update | Eilidh Turner | 2026-08-24 | Done
6 | Factory acceptance test report – approval | Eilidh Turner | 2026-06-27 | In progress