## Register
Drawing no. | Title | Project | Discipline | Rev | Status | Date | Originator | Format
HB-ELE-DWG-0101 | Offshore substation single line diagram | HB | ELE | 3 | IFC | 2026-05-11 | Weyland | SVG/PDF
HB-ELE-DWG-0102 | Onshore substation Harrow Bay East single line diagram | HB | ELE | 2 | IFC | 2026-03-02 | Weyland | DWG
HB-ELE-DWG-0110 | Array cable layout – strings S1–S8 | HB | ELE | 4 | IFC | 2026-06-19 | Severn Subsea Cables | DWG
HB-ELE-DWG-0120 | Export cable route – KP0 to KP62 | HB | ELE | 5 | IFC | 2026-08-04 | Severn Subsea Cables | DWG
HB-CIV-DWG-0201 | Monopile general arrangement – province A | HB | CIV | 2 | IFC | 2025-12-08 | Rhenus Steelworks | DWG
HB-CIV-DWG-0202 | Monopile general arrangement – province B | HB | CIV | 2 | IFC | 2025-12-08 | Rhenus Steelworks | DWG
HB-CIV-DWG-0203 | Monopile general arrangement – province C | HB | CIV | 2 | IFC | 2025-12-15 | Rhenus Steelworks | DWG
HB-CIV-DWG-0204 | Monopile general arrangement – province D | HB | CIV | 3 | IFC | 2026-02-27 | Rhenus Steelworks | DWG
HB-CIV-DWG-0210 | Transition piece general arrangement | HB | CIV | 2 | IFC | 2025-12-15 | Rhenus Steelworks | DWG
HB-CIV-DWG-0215 | Boat landing and access platform | HB | CIV | 1 | IFC | 2026-01-21 | Rhenus Steelworks | DWG
HB-CIV-DWG-0230 | Scour protection layout | HB | CIV | 1 | IFC | 2026-03-10 | Weyland | DWG
HB-GEN-DWG-0001 | Wind farm layout – final coordinates | HB | GEN | 6 | IFC | 2025-09-22 | Weyland | DWG/GIS
HB-GEN-DWG-0005 | Micro-siting WTG 22 and WTG 31 | HB | GEN | 1 | IFC | 2025-10-14 | Weyland | DWG
HB-OSS-DWG-0300 | OSS topside general arrangement | HB | OSS | 4 | As built | 2026-09-10 | OSS contractor | DWG
HB-OSS-DWG-0310 | OSS jacket general arrangement | HB | OSS | 3 | As built | 2026-07-30 | OSS contractor | DWG
KR-ELE-DWG-0012 | Wind farm single line diagram (as built) | KR | ELE | 2 | As built | 2024-05-02 | Weyland | ODG
KR-ELE-DWG-0015 | 33 kV collector cable routes | KR | ELE | 2 | As built | 2024-05-02 | BoP contractor | DWG
KR-CIV-DWG-0101 | Access tracks and crane pads | KR | CIV | 3 | As built | 2024-04-11 | BoP contractor | DWG
KR-CIV-DWG-0110 | Turbine foundation T-01 to T-18 | KR | CIV | 2 | As built | 2024-04-11 | BoP contractor | DWG
MB-GEN-DWG-0001 | Site layout – planning issue | MB | GEN | D | Planning | 2026-06-05 | Weyland | DWG/PDF
MB-GEN-DWG-0002 | Landscape and biodiversity plan | MB | GEN | C | Planning | 2026-06-05 | Landscape architect | PDF
MB-ELE-DWG-0003 | Plant single line diagram – planning issue | MB | ELE | B | Planning | 2026-05-26 | Weyland | SVG/PDF
MB-CIV-DWG-0010 | Construction access via Mill Lane – swept path | MB | CIV | B | Planning | 2026-05-12 | Transport consultant | PDF
FW-GEN-DWG-0001 | Concept layout 100 MW / 200 MWh | FW | GEN | A | Concept | 2026-08-21 | Weyland | SVG
H2-GEN-DWG-0001 | Electrolyser site layout – Port of Eastholm | H2 | GEN | B | Concept | 2026-08-14 | Weyland | SVG

## Status codes
Code | Meaning
Concept | For information, not for design
Planning | Submitted with planning application
IFC | Issued for construction
As built | Reflects installed condition