Kestrel Ridge – Lessons Learned Workshop

T-07 gearbox failure and first two years of operation

Sofie Lindqvist  ·  20 February 2026

Date: 19 February 2026, Edinburgh office and video  
Participants: Sofie Lindqvist (chair), David Chen, Ben Okoye, Sara Lindgren, Patrick Doyle, Mei Tanaka; Highline Wind Services (2 people)

# 1. What happened

On 14 January 2026 the condition monitoring system of T-07 flagged high-speed shaft bearing vibration. The turbine tripped the same afternoon. Inspection confirmed a bearing failure in the gearbox (incident KR-INC-2026-003). The gearbox was exchanged under warranty; T-07 returned to service after 23 days.

# 2. What went well

CMS detection worked and the turbine was stopped before secondary damage.

Warranty claim accepted within one week thanks to complete oil analysis records.

No safety incidents during the exchange despite winter conditions.

# 3. What could be better

Crane mobilisation took 11 days – the main driver of downtime.

Snow on the access track delayed the crane by two days; snow clearance contract not in place.

CMS alarm thresholds were factory defaults; an earlier warning was possible in December.

# 4. Actions

| # | Action | Owner | Due |
| --- | --- | --- | --- |
| 1 | Framework agreement for heavy crane with 10-day call-off | David Chen | 2026-05-31 |
| 2 | Winter access plan incl. snow clearance contract | Ben Okoye | 2026-10-31 |
| 3 | Review CMS alarm thresholds for all 18 turbines | Sara Lindgren | 2026-04-30 |
| 4 | Add lesson to company database (LL-0028) | Sofie Lindqvist | 2026-02-28 |