Harrow Bay Offshore Wind – Final Investment Decision

Board paper for the extraordinary meeting of the Supervisory Board, 12 February 2026

Dr. Amara Okafor  ·  05 February 2026  ·  WE-SB-2026-02-FID

# 1. Decision requested

The Executive Board requests the Supervisory Board to approve the final investment decision (FID) for Harrow Bay Offshore Wind (480 MW) with a total capital expenditure budget of EUR 1,620 m, the execution of the finance documents for EUR 1,100 m senior debt arranged by Hanseatic Infrastructure Bank, and a capital increase of EUR 140 m. Financial close is planned for the same day, 12 February 2026.

# 2. The project

| Item | Value |
| --- | --- |
| Location | UK North Sea, 38 km off the coast of Harrow Bay |
| Capacity | 480 MW |
| Turbines | 40 × Halden HTS-12 (12 MW), rotor diameter 236 m, hub height 140 m |
| Foundations | Monopiles, 9.5 m diameter, water depth 28–36 m |
| Grid connection | 2 × 220 kV export cables, 62 km each, to onshore substation Harrow Bay East |
| Expected generation | 1.9 TWh per year (P50), equivalent to 520,000 homes |
| Development consent | Granted 20 November 2023 |
| Construction start | April 2026 (first monopile) |
| Commercial operation (COD) | 30 June 2028 |

# 3. Capital expenditure

| Package | EUR m |
| --- | --- |
| Wind turbines – Halden Turbine Systems (WE-CON-2025-022) | 575 |
| Monopiles and transition pieces – Rhenus Steelworks (WE-CON-2025-027) | 268 |
| Export and array cables – Severn Subsea Cables (WE-CON-2025-031) | 232 |
| Offshore substation HB-OSS – Norfab Offshore Structures (WE-CON-2025-035) | 196 |
| Marine installation, MV Sea Atlas charter (WE-CON-2025-040), port and logistics | 122 |
| Onshore substation Harrow Bay East and grid works (WE-CON-2025-044) | 61 |
| Development, owner's costs, project management and insurance | 111 |
| Contingency (3.5 % of base capex) | 55 |
| Total capex | 1,620 |

Capex budget at FID, nominal, including contingency

Around 87 % of the base capex is fixed under signed EPCI-type supply and installation contracts. The remaining exposure relates to vessel weather downtime, onshore civil works and owner's costs. The contingency of EUR 55 m was sized with a Monte Carlo analysis at P80; a further EUR 45 m of standby equity is committed by the shareholders.

# 4. Financing

| Lender | Role | EUR m |
| --- | --- | --- |
| Hanseatic Infrastructure Bank | Mandated lead arranger, facility and security agent | 350 |
| Nordvik Export Finance (ECA-covered tranche) | Lender | 300 |
| Elbe Commercial Bank | Lender | 200 |
| Caledonia Capital Bank plc | Lender | 150 |
| Lindwurm Infrastructure Debt Fund II | Institutional lender | 100 |
| Total senior debt |  | 1,100 |

Facility: EUR 1,100 m senior secured construction and term loan facility

Financial close: 12 February 2026

Tenor: Construction period plus 18 years after COD (final maturity 2046)

Margin: 165 bps during construction, 150–190 bps step-up during operations

Interest hedging: 85 % of the expected debt hedged with amortising swaps at 2.74 % (5 counterparties)

Debt : equity: 68 : 32 (EUR 1,100 m debt / EUR 520 m equity)

Equity first: Yes – equity of EUR 520 m fully contributed before first debt drawdown

DSCR covenant: Lock-up 1.15x, default 1.05x (historic and projected, P90)

Sizing DSCR: 1.30x P90 / 1.40x P50

Contingency: EUR 96 m contingency in the budget plus EUR 45 m standby equity

Revenue support: 15-year PPA WE-PPA-2026-004 with Arcturus Steel AG for 150 MW plus CfD for the remaining capacity

Lenders' technical adviser: Strandberg Technical Advisory

# 5. Returns

| Metric | P50 | P90 |
| --- | --- | --- |
| Project IRR (post-tax, nominal) | 7.6 % | 6.4 % |
| Equity IRR (post-tax, nominal) | 10.4 % | 8.1 % |
| Minimum DSCR | 1.40x | 1.30x |
| Payback (from COD) | 11.2 years | 13.5 years |
| Levelised cost of energy | EUR 71 / MWh | EUR 79 / MWh |

The equity IRR exceeds the hurdle rate of 9.0 % for contracted offshore wind set in the investment policy. Around 42 % of the P50 output is sold under the 15-year PPA with Arcturus Steel AG, which is expected to be signed in the first half of 2026; the remainder benefits from a contract for difference. A 20 % decline of merchant prices in the post-CfD tail reduces the equity IRR by 0.7 percentage points.

# 6. Key risks

| Risk | Mitigation | Rating |
| --- | --- | --- |
| Supply chain – export cable manufacturing | Factory acceptance tests witnessed by owner's engineer; delay LDs under WE-CON-2025-031; 14 weeks float to COD | Medium |
| Weather downtime during installation | P75 weather allowance in schedule; MV Sea Atlas charter with extension option | Medium |
| Marine mammals and seabirds | Bubble curtains, seasonal piling restrictions, monitoring by Marlow Ecology | Low |
| Interest rates | 85 % hedged at 2.74 % at financial close | Low |
| Grid connection by NordGrid Transmission | Connection agreement signed; onshore works started 2025 | Low |

# 7. Conditions precedent

Credit approvals of all five lenders (received 3 February 2026)

Lenders' technical adviser Strandberg Technical Advisory – final report without material findings

Model audit by Keller & Rowe – clean opinion

Insurance programme placed (construction all risks, delay in start-up)

Capital increase of EUR 140 m subscribed

# 8. Recommendation

The Executive Board unanimously recommends approving the final investment decision for Harrow Bay Offshore Wind. Harrow Bay will add 480 MW to our operating capacity, increase group EBITDA by an expected EUR 150–160 m per year from 2029, and is the cornerstone of our Strategy 2030.