Minutes – DRAFT

Supervisory Board of Weyland Energy GmbH – Q3 meeting

Dr. Amara Okafor  ·  01 October 2026  ·  WE-SB-MIN-2026-09

| Meeting | Supervisory Board – Q3 meeting |
| --- | --- |
| Date | 24 September 2026 |
| Place | Hamburg HQ, Am Sandtorkai 41 |
| Chair | Dr. Karin Albrecht |
| Minutes | Lukas Meyer (Board Secretary) |

# Present

Dr. Karin Albrecht (Chair of the Supervisory Board)

Michael Sørensen (Deputy Chair (Nordlicht Infrastructure Partners))

Prof. Dr. Ulrike Brandes (Independent member, Chair of the Audit Committee)

Gareth Hughes (Independent member, offshore wind expert)

Silke Hamann (Employee representative)

Dr. Amara Okafor (CEO)

Jonas Richter (CFO)

Paul Wagner (COO)

The Chair opened the meeting at 10:00, welcomed the members and confirmed that the meeting was duly convened and quorate.

# Agenda items

## 1. Approval of the minutes of 25 June 2026

The minutes of the previous meeting were approved without changes.

## 2. Harrow Bay – progress and HB-RISK-017 export cable 2 delay

Elena Márquez (invited) presented the status: 13 of 40 monopiles installed by 22 September, offshore substation topside installed on 19 August. Severn Subsea Cables re-manufactures a 9 km section of export cable 2 after the factory test failure of 21 July. Gareth Hughes asked whether liquidated damages cover the standby costs; Priya Nair confirmed delay LDs of up to EUR 11.2 m under WE-CON-2025-031. Katarzyna Nowak reported ISO 27001 readiness at 68 % of controls implemented.

## 3. Forecast 3 (8+4) and budget process 2027

Forecast 3 (8+4) projects revenue of EUR 330.5 m and EBITDA of EUR 151.9 m versus a budget of EUR 334 m / EUR 156 m. Year-to-date August revenue EUR 207.1 m (budget EUR 210.2 m), EBITDA EUR 86.4 m (budget EUR 90.1 m).

## 4. Green Hydrogen Pilot – feasibility study and EU Innovation Fund application

The board took note of the report and the documents provided in the board pack. No further questions were raised.

## 5. Information security – ISO 27001 readiness

The board took note of the report and the documents provided in the board pack. No further questions were raised.

## 6. North Sea Energy Summit 2026 – feedback

The board took note of the report and the documents provided in the board pack. No further questions were raised.

# Resolutions

The board took note of HB-RISK-017 and the resequenced cable lay campaign; COD of 30 June 2028 remains achievable with float reduced from 14 to 6 weeks.

The board approved the submission of an EU Innovation Fund application for the 5 MW electrolyser at Port of Eastholm (co-funding request EUR 9.8 m).

Budget process 2027 and the board calendar 2027 were approved.

# Actions

| Action | Owner | Due |
| --- | --- | --- |
| Draft budget 2027 | Jonas Richter | 2026-12-10 |
| Monthly update on export cable 2 re-manufacture | Elena Márquez | monthly |
| Stage 1 audit ISO 27001 – date confirmation | Katarzyna Nowak | 2026-11-30 |

There being no further business, the Chair closed the meeting.