## Actions
# | Date raised | Action | Owner | Due | Status
1 | 2026-07-06 | Prepare Severn Subsea Cables escalation call | Elena Márquez | 2026-07-24 | Done
2 | 2026-07-27 | Written resolution contingency release HB-RISK-017 | Jonas Richter | 2026-08-06 | Done
3 | 2026-08-03 | Communication plan Arcturus: impact of cable delay on PPA (none) | Noah Fischer | 2026-08-14 | Done
4 | 2026-08-10 | Budget 2027 guidelines | Jonas Richter | 2026-09-30 | Done
5 | 2026-08-17 | Keynote North Sea Energy Summit | Dr. Amara Okafor | 2026-09-22 | Done
6 | 2026-08-24 | Hydrogen – EU Innovation Fund application draft | Sofie Lindqvist | 2026-10-15 | Open
7 | 2026-08-31 | ISO 27001 – stage 1 audit date | Katarzyna Nowak | 2026-11-30 | Open
8 | 2026-09-07 | Leadership programme cohort 2 nominations | Julia Hoffmann | 2026-10-09 | Open
9 | 2026-09-14 | Millbrook – response to consultee comments | Liam McAllister | 2026-10-16 | Open
10 | 2026-09-21 | Lessons learned HSE-INC-2026-018 – contractor forum | Hannah Weber | 2026-10-20 | Open
11 | 2026-09-28 | Minutes SB 24 Sep – final review | Dr. Amara Okafor | 2026-10-05 | Open
12 | 2026-09-28 | Kestrel Ridge O&M contract WE-CON-2023-015 – extension options | David Chen | 2026-11-13 | Open