## Plan
ID | Task | Owner | Start | Finish | Status | Dependency
1 | Site screening and selection | Kwame Mensah | 2025-10-01 | 2025-12-19 | Complete
2 | Investment Committee – development budget | Liam McAllister | 2026-01-05 | 2026-03-04 | Complete | 1
3 | Land option negotiation and signature | Kwame Mensah | 2026-01-12 | 2026-04-30 | Complete | 1
4 | Grid connection application | Ahmed Rahimi | 2026-05-04 | 2026-07-15 | Complete | 3
5 | Revenue stack and route-to-market study | Kwame Mensah | 2026-05-25 | 2026-10-30 | In progress
6 | Concept layout and design basis | Sofie Lindqvist | 2026-07-20 | 2026-10-16 | In progress | 3
7 | Fire service pre-application consultation | Liam McAllister | 2026-11-02 | 2026-12-18 | Not started | 6
8 | Grid connection offer received | NordGrid Transmission | 2027-04-01 | 2027-06-30 | Not started | 4
9 | Environmental surveys (ecology, noise, archaeology) | Liam McAllister | 2027-03-01 | 2027-09-30 | Not started
10 | Community consultation | Tom Berger | 2027-05-10 | 2027-07-16 | Not started | 6
11 | Planning application submission | Liam McAllister | 2027-10-01 | 2027-10-29 | Not started | 8,9,10
12 | Planning decision | Local planning authority | 2027-11-01 | 2028-03-31 | Not started | 11
13 | Integrator and BoP tender | Laura Kessler | 2027-09-01 | 2028-04-28 | Not started | 8
14 | Financing and FID | Jonas Richter | 2028-03-01 | 2028-07-31 | Not started | 12,13
15 | Construction | EPC / integrator | 2028-08-01 | 2029-08-31 | Not started | 14
16 | Commissioning and COD | Liam McAllister | 2029-08-01 | 2029-09-30 | Not started | 15

## Milestones
Milestone | Date | Status
Land option signed | 2026-04-30 | Achieved
Grid application submitted | 2026-07-15 | Achieved
Grid offer | Q2 2027 | Expected
Planning submission | Q4 2027 | Planned
FID | Q3 2028 | Planned
COD | 2029-09-30 | Target