Fenwick Battery Storage – Project Kick-off

Minutes, 10 March 2026

Liam McAllister  ·  11 March 2026

Participants: Liam McAllister (chair), Kwame Mensah, Sofie Lindqvist, Priya Nair, Ahmed Rahimi, Marcus Bell

# 1. Mandate

The Investment Committee released a development budget of EUR 900,000 on 4 March 2026 to take Fenwick to a grid offer and a planning submission. Next IC gate: after the grid offer (Q2 2027).

# 2. Roles

| Role | Name |
| --- | --- |
| Project manager | Liam McAllister |
| Project lead / developer | Kwame Mensah |
| Engineering | Sofie Lindqvist, Mei Tanaka |
| Grid | Ahmed Rahimi |
| Legal | Priya Nair, Lukas Meyer |
| Finance | Marcus Bell |

# 3. Decisions

Target option signature by end of April 2026.

Apply for 100 MW / 200 MWh – 2-hour duration.

Use this space for all project documents; land documents restricted to Legal and project lead.

# 4. Actions

| Action | Owner | Due |
| --- | --- | --- |
| Finalise heads of terms with Hallam Farms | Kwame Mensah | 2026-03-20 |
| Instruct solicitors for option agreement | Priya Nair | 2026-03-17 |
| Start grid application pack | Ahmed Rahimi | 2026-05-04 |
| Commission two market forecasts | Kwame Mensah | 2026-05-15 |