## Requirements
Req. | Topic | Trigger | Submitted | Discharged | Status | Owner
1 | Phasing plan | Pre-commencement | 2024-03-17 | 2024-04-27 | Discharged | Felix Brandt
2 | Construction method statement | Pre-commencement | 2024-04-22 | 2024-08-05 | Discharged | Clara Neumann
3 | Onshore CEMP | Pre-commencement | 2024-05-21 | 2024-07-17 | Discharged | Charlotte Dubois
4 | Code of construction practice | Pre-commencement | 2024-06-14 | 2024-08-22 | Discharged | Charlotte Dubois
5 | Construction traffic plan | Pre-commencement | 2024-07-23 | 2024-10-06 | Discharged | Clara Neumann
6 | Archaeology written scheme | Pre-commencement | 2024-08-13 | 2024-09-28 | Discharged | Felix Brandt
7 | Landscape plan (substation) | Pre-commencement | 2024-09-15 | 2024-11-08 | Discharged | Charlotte Dubois
8 | Surface water drainage | Pre-commencement | 2024-10-22 | 2025-01-04 | Discharged | Charlotte Dubois
9 | Piling marine mammal mitigation plan | Pre-commencement | 2024-11-18 | 2025-03-01 | Discharged | Charlotte Dubois
10 | Cable specification and installation plan | Pre-commencement | 2024-12-22 | 2025-02-27 | Discharged | Charlotte Dubois
11 | Navigation and lighting plan | Pre-commencement | 2025-01-22 | 2025-03-27 | Discharged | Felix Brandt
12 | Fisheries liaison and coexistence plan | Pre-commencement | 2025-02-26 | 2025-05-09 | Discharged | Charlotte Dubois
13 | Ornithological monitoring plan | Pre-operation | 2025-03-12 | 2025-05-28 | Discharged | Felix Brandt
14 | Noise monitoring (onshore) | Pre-operation | 2025-04-15 | 2025-05-27 | Discharged | Clara Neumann
15 | Skills and employment plan | Pre-operation | 2025-05-22 | 2025-09-01 | Discharged | Clara Neumann
16 | Decommissioning programme | Pre-operation |  |  | Pre-operation | Felix Brandt
17 | Aviation radar mitigation | Pre-operation |  |  | Pre-operation | Clara Neumann
18 | Operational noise | Pre-operation |  |  | Pre-operation | Clara Neumann
19 | Ecological management plan (landfall) | Pre-operation |  |  | Ongoing | Felix Brandt
20 | Public rights of way (landfall) | Pre-operation |  |  | Ongoing | Clara Neumann