## Connections
Project | Agreement / offer | Type | Point of connection | Voltage (kV) | Export (MW) | Import (MW) | Status | Connection date | Securities (EUR m) | Owner
Harrow Bay Offshore Wind | NGT-BCA-2023-0088 | Bilateral connection agreement | Harrow Bay East 400 kV substation | 400 | 480 | 15 | Signed – construction | 2027-09-01 (phase 1) / 2028-03-31 (full) | 12.6 | Ahmed Rahimi
Kestrel Ridge Wind Farm | NGT-CA-2021-0213 | Connection agreement | Kestrel Ridge 132 kV substation | 132 | 75.6 | 2 | Operational | 2024-01-29 | 0 | Ahmed Rahimi
Millbrook Solar & Storage | NGT-OFF-2025-1187 | Connection offer (accepted) | Millbrook 132 kV substation | 132 | 70 | 20 | Accepted 2025-12-12 | 2028-10-31 | 0.6 | Ahmed Rahimi
Fenwick Battery Storage | NGT-APP-2026-0739 | Connection application | Fenwick 132 kV substation | 132 | 100 | 100 | Application submitted 2026-07-15 | Offer expected Q2 2027 | 0 | Ahmed Rahimi
Green Hydrogen Pilot | — | Demand connection (pre-application) | Port of Eastholm 33 kV | 33 | 0 | 5 | Pre-application | tbc | 0 | Ahmed Rahimi
Total

## Milestones
Project | Milestone | Contract date | Forecast | Status
Harrow Bay | Onshore substation civils complete | 2026-06-30 | 2026-06-24 | Done
Harrow Bay | NordGrid 400 kV bay ready for energisation | 2027-06-30 | 2027-06-30 | On track
Harrow Bay | Export cable 1 energised | 2027-09-01 | 2027-09-01 | On track
Harrow Bay | Export cable 2 energised | 2027-11-30 | 2028-01-25 | At risk – HB-RISK-017
Harrow Bay | Full export capacity 480 MW | 2028-03-31 | 2028-03-31 | On track (float used)
Millbrook | Securities step-up at planning consent | Consent + 30 days | Q1 2027 | Pending
Millbrook | NordGrid supergrid transformer 2 | 2028-06-30 | 2028-05-15 | On track
Millbrook | Connection date | 2028-10-31 | 2028-10-31 | On track
Fenwick | Application competent (NordGrid) | 2026-08-28 | 2026-08-21 | Done
Fenwick | Gate 2 evidence submission | 2026-11-30 | 2026-11-30 | In progress
Fenwick | Offer issued | Q2 2027 | Q2 2027 | Awaiting NordGrid