## Register
Risk ID | Title | Category | Owner | Probability (1-5) | Impact (1-5) | Score | Rating | Mitigation | Status | Trend | Last review
HB-RISK-001 | Adverse weather reduces monopile installation rate below plan | Schedule | Felix Brandt | 4 | 4 |  | High | Weather-window planning with 72 h forecasts; charter option 2 exercised; 24/7 piling where consent allows | Open | ↑ | 2026-09-29
HB-RISK-002 | Piling noise exceeds consent limit of 160 dB SEL at 750 m | Environment | Clara Neumann | 2 | 4 |  | Medium | Double big bubble curtain, soft-start, hammer energy management, real-time hydrophone monitoring | Open | → | 2026-09-29
HB-RISK-003 | Seasonal piling restriction extended by regulator | Consent | Charlotte Dubois | 2 | 4 |  | Medium | Early engagement with regulator; monitoring data shared monthly by Marlow Ecology | Open | → | 2026-09-29
HB-RISK-004 | Delay to HTS-12 nacelle deliveries from Halden Turbine Systems | Supply chain | Elena Márquez | 2 | 5 |  | Medium | Monthly production reviews in Aarhus; LDs under WE-CON-2025-022; expediting visits | Open | → | 2026-09-29
HB-RISK-005 | Monopile fabrication quality issues at Rhenus Steelworks | Quality | Felix Brandt | 2 | 3 |  | Low | Resident inspector at yard; receiving inspection at Eastholm; NCR process | Open | ↓ | 2026-09-29
HB-RISK-006 | Unexpected boulders or soft soils at monopile positions | Technical | Oliver Grant | 3 | 3 |  | Medium | Pre-installation CPT at every position; drive-drill contingency spread on standby | Open | → | 2026-09-29
HB-RISK-007 | Pile refusal before target penetration | Technical | Oliver Grant | 2 | 4 |  | Medium | Driveability analysis per position; larger hammer option | Open | ↓ | 2026-09-29
HB-RISK-008 | MV Sea Atlas major breakdown (crane / jacking system) | Schedule | Felix Brandt | 2 | 5 |  | Medium | Planned maintenance in July restriction window; critical spares on board | Open | → | 2026-09-29
HB-RISK-009 | Dropped object during lifting operations | HSE | Yusuf Demir | 2 | 5 |  | Medium | DROPS programme, secondary retention checks, exclusion zones (see HSE-INC-2026-018) | Open | ↓ | 2026-09-29
HB-RISK-010 | Person overboard during crew transfer | HSE | Yusuf Demir | 1 | 5 |  | Low | Walk-to-work where possible; CTV transfer limits Hs 1.5 m; MOB drills monthly | Open | → | 2026-09-29
HB-RISK-011 | Fishing gear conflicts in construction area | Stakeholder | Grace Mitchell | 3 | 2 |  | Low | Fisheries Liaison Officer, guard vessels, weekly Notices to Mariners | Open | → | 2026-09-29
HB-RISK-012 | Unexploded ordnance (UXO) found on cable route | Technical | Mei Tanaka | 2 | 4 |  | Medium | UXO survey complete; target investigation ahead of cable lay; route micro-siting | Open | → | 2026-09-29
HB-RISK-013 | Port of Eastholm quay capacity insufficient during 2027 turbine pre-assembly | Logistics | Ingrid Solberg | 3 | 3 |  | Medium | Quay 3 reserved; storage agreement extension; just-in-time delivery plan with Halden | Open | → | 2026-09-29
HB-RISK-014 | Grid connection works at Harrow Bay East delayed by NordGrid Transmission | Grid | Ahmed Rahimi | 2 | 5 |  | Medium | Monthly interface meetings; energisation date contractually fixed 2027-08-15 | Open | → | 2026-09-29
HB-RISK-015 | Steel price escalation on remaining procurement | Commercial | Laura Kessler | 2 | 2 |  | Low | Major packages fixed price; indexation only on secondary steel | Closed | – | 2026-09-29
HB-RISK-016 | FX exposure GBP/EUR on UK-denominated contracts | Financial | Marcus Bell | 3 | 2 |  | Low | Hedging programme per treasury policy (80 % hedged to 2028) | Open | → | 2026-09-29
HB-RISK-017 | 8-week delay of export cable 2 delivery from Severn Subsea Cables (factory test failure, re-manufacture of 9 km section) | Supply chain | Elena Márquez | 5 | 4 |  | High | Resequence cable lay campaign (export cable 1 first, array strings A/B earlier); liquidated damages under WE-CON-2025-031; weekly expediting; first power via export cable 1 | Open – materialised | ↑ | 2026-09-29
HB-RISK-018 | Cable lay vessel availability after resequencing | Schedule | Mei Tanaka | 3 | 4 |  | Medium | Severn to confirm vessel slot for August 2027 by 31 Oct 2026 | Open | ↑ | 2026-09-29
HB-RISK-019 | Seabird displacement above consented assumptions | Environment | Clara Neumann | 2 | 3 |  | Low | Pre-, during- and post-construction surveys by Marlow Ecology | Open | → | 2026-09-29
HB-RISK-020 | Marine mammal injury during piling | Environment | Clara Neumann | 1 | 5 |  | Low | MMO and PAM, 30-min pre-piling search, acoustic deterrent devices, soft start | Open | → | 2026-09-29
HB-RISK-021 | Interface between TP flange and HTS-12 tower out of tolerance | Technical | Sofie Lindqvist | 2 | 4 |  | Medium | Flange flatness measured after installation at every TP; Halden sign-off | Open | ↓ | 2026-09-29
HB-RISK-022 | Insurance claim disputes for weather standby | Commercial | Priya Nair | 2 | 2 |  | Low | Weather risk allocated in charter; standby rates agreed | Open | → | 2026-09-29
HB-RISK-023 | Key personnel turnover in project team | Organisation | Elena Márquez | 2 | 3 |  | Low | Succession plan, deputies for all package managers, retention bonus at COD | Open | → | 2026-09-29
HB-RISK-024 | OSS topside lift weather window missed | Schedule | Mei Tanaka | 3 | 4 |  | Medium | Two lift windows contracted | Closed | – | 2026-09-29
HB-RISK-025 | Lender drawdown conditions not met on time | Financial | Marcus Bell | 1 | 4 |  | Low | Monthly LTA site reports; conditions tracker | Open | → | 2026-09-29
HB-RISK-026 | Cyber incident affecting project document control or SCADA build | IT | Katarzyna Nowak | 2 | 3 |  | Low | MFA, segregated OT network design, supplier security clauses | Open | → | 2026-09-29
HB-RISK-027 | Archaeological find on cable route | Consent | Charlotte Dubois | 1 | 3 |  | Low | Written scheme of investigation, archaeological exclusion zones | Open | → | 2026-09-29
HB-RISK-028 | Community opposition to onshore cable route works | Stakeholder | Tom Berger | 2 | 2 |  | Low | Community liaison, newsletter, construction traffic plan | Open | ↓ | 2026-09-29
HB-RISK-029 | Monopile campaign extends into winter 2026/27 | Schedule | Felix Brandt | 4 | 4 |  | High | Charter option 2, winter weather limits review with Atlas Marine, second hammer | Open | ↑ | 2026-09-29
HB-RISK-030 | Turbine installation vessel slot for March 2027 at risk if foundations late | Schedule | Elena Márquez | 3 | 5 |  | High | Foundation recovery plan; sequence turbine installation on string A first | Open | ↑ | 2026-09-29

## Heat Map
Probability \ Impact | 1 | 2 | 3 | 4 | 5
5 | 0 | 0 | 0 | 1 | 0
4 | 0 | 0 | 0 | 2 | 0
3 | 0 | 2 | 2 | 1 | 1
2 | 0 | 2 | 4 | 5 | 4
1 | 0 | 0 | 1 | 1 | 2

## Scoring Guide
Score | Probability | Impact (cost) | Impact (schedule)
1 | < 5 % | < EUR 0.5 m | < 1 week
2 | 5–20 % | EUR 0.5–2 m | 1–2 weeks
3 | 20–50 % | EUR 2–5 m | 2–4 weeks
4 | 50–80 % | EUR 5–15 m | 1–3 months
5 | > 80 % / materialised | > EUR 15 m | > 3 months or COD at risk