## Milestones
ID | Milestone | Baseline Rev 2 | Forecast / Actual | Variance (days) | Status
M01 | Development consent granted | 2023-11-20 | 2023-11-20 |  | Achieved
M02 | TSA signed – WE-CON-2025-022 | 2025-06-30 | 2025-06-30 |  | Achieved
M03 | FID and financial close | 2026-02-12 | 2026-02-12 |  | Achieved
M04 | First monopile installed (HB-A01) | 2026-04-07 | 2026-04-07 |  | Achieved
M05 | OSS jacket installed | 2026-06-25 | 2026-06-27 |  | Achieved
M06 | OSS topside installed | 2026-08-14 | 2026-08-19 |  | Achieved
M07 | String A foundations complete (14) | 2026-09-04 | 2026-09-30 |  | Achieved
M08 | String B foundations complete (27) | 2026-12-04 | 2026-12-18 |  | At risk
M09 | Last monopile installed (40) | 2027-02-12 | 2027-02-26 |  | At risk
M10 | Export cable 1 delivered | 2026-12-11 | 2026-12-11 |  | On track
M11 | Export cable 2 delivered | 2027-01-15 | 2027-03-12 |  | Delayed
M12 | First turbine installed | 2027-03-01 | 2027-03-01 |  | On track
M13 | Grid energisation Harrow Bay East | 2027-08-15 | 2027-08-15 |  | On track
M14 | First power | 2027-09-30 | 2027-09-30 |  | On track
M15 | Export cable 2 energised | 2027-07-31 | 2027-09-30 |  | Delayed
M16 | Last turbine installed | 2028-03-31 | 2028-03-31 |  | On track
M17 | Commercial operation date (COD) | 2028-06-30 | 2028-06-30 |  | On track

## Activities
WBS | Activity | Responsible | Baseline start | Baseline finish | Forecast finish | % complete
1.1 | Project management & controls | Elena Márquez | 2026-02-12 | 2028-06-30 | 2028-06-30 | 31%
2.1 | Monopile & TP fabrication (Rhenus) | Felix Brandt | 2025-10-01 | 2026-12-18 | 2026-12-18 | 78%
2.2 | Monopile installation – string A | Felix Brandt | 2026-04-07 | 2026-09-04 | 2026-09-30 | 100%
2.3 | Monopile installation – string B | Felix Brandt | 2026-09-07 | 2026-12-04 | 2026-12-18 | 0%
2.4 | Monopile installation – string C | Felix Brandt | 2026-12-07 | 2027-02-12 | 2027-02-26 | 0%
2.5 | TP bolt tensioning & flange survey | Felix Brandt | 2026-04-09 | 2027-02-26 | 2027-03-12 | 33%
3.1 | OSS fabrication | Mei Tanaka | 2025-09-01 | 2026-06-15 | 2026-06-19 | 100%
3.2 | OSS installation (jacket + topside) | Mei Tanaka | 2026-06-22 | 2026-08-14 | 2026-08-19 | 100%
3.3 | OSS hook-up & commissioning | Mei Tanaka | 2026-08-24 | 2027-06-30 | 2027-06-30 | 8%
4.1 | Export cable 1 manufacture & test | Mei Tanaka | 2026-02-01 | 2026-12-11 | 2026-12-11 | 82%
4.2 | Export cable 2 manufacture & test | Mei Tanaka | 2026-04-01 | 2027-01-15 | 2027-03-12 | 61%
4.3 | Landfall HDD | Mei Tanaka | 2026-05-04 | 2026-08-28 | 2026-08-28 | 100%
4.4 | Export cable 1 lay & burial | Mei Tanaka | 2027-04-15 | 2027-06-30 | 2027-06-30 | 0%
4.5 | Array cables strings A/B | Mei Tanaka | 2027-05-01 | 2027-08-31 | 2027-07-31 | 0%
4.6 | Export cable 2 lay & burial | Mei Tanaka | 2027-06-01 | 2027-07-31 | 2027-09-30 | 0%
5.1 | Onshore substation Harrow Bay East | Ahmed Rahimi | 2026-03-02 | 2027-07-30 | 2027-07-30 | 44%
5.2 | Grid connection (NordGrid Transmission) | Ahmed Rahimi | 2026-03-02 | 2027-08-15 | 2027-08-15 | 38%
6.1 | Turbine manufacture (Halden) | Elena Márquez | 2026-03-01 | 2027-11-30 | 2027-11-30 | 12%
6.2 | Turbine pre-assembly Port of Eastholm | Ingrid Solberg | 2027-01-11 | 2028-02-28 | 2028-02-28 | 0%
6.3 | Turbine installation | Felix Brandt | 2027-03-01 | 2028-03-31 | 2028-03-31 | 0%
7.1 | Commissioning & reliability run | Mei Tanaka | 2027-09-30 | 2028-06-15 | 2028-06-15 | 0%
8.1 | Environmental monitoring (construction phase) | Clara Neumann | 2026-03-01 | 2028-06-30 | 2028-06-30 | 27%

## Monopile Sequence
Position | Water depth (m) | Baseline date | Actual / forecast | Status
HB-A01 | 28.6 | 2026-04-07 | 2026-04-07 | Installed
HB-A02 | 29.3 | 2026-04-15 | 2026-04-12 | Installed
HB-A03 | 29.6 | 2026-04-23 | 2026-04-18 | Installed
HB-A04 | 30.3 | 2026-05-01 | 2026-04-25 | Installed
HB-A05 | 30.6 | 2026-05-09 | 2026-05-03 | Installed
HB-A06 | 31.3 | 2026-05-17 | 2026-05-12 | Installed
HB-A07 | 32 | 2026-05-25 | 2026-05-21 | Installed
HB-A08 | 32.3 | 2026-06-02 | 2026-05-30 | Installed
HB-A09 | 33 | 2026-06-10 | 2026-06-14 | Installed
HB-A10 | 33.4 | 2026-06-18 | 2026-06-24 | Installed
HB-A11 | 34.1 | 2026-06-25 | 2026-08-06 | Installed
HB-A12 | 34.8 | 2026-07-03 | 2026-08-23 | Installed
HB-A13 | 35.1 | 2026-07-11 | 2026-09-11 | Installed
HB-A14 | 35.8 | 2026-07-19 | 2026-09-30 | Installed
HB-B01 | 30.3 | 2026-07-27 | 2026-10-07 | Planned
HB-B02 | 30.8 | 2026-08-04 | 2026-10-14 | Planned
HB-B03 | 31 | 2026-08-12 | 2026-10-19 | Planned
HB-B04 | 31.6 | 2026-08-20 | 2026-10-25 | Planned
HB-B05 | 31.8 | 2026-08-28 | 2026-11-01 | Planned
HB-B06 | 32.4 | 2026-09-05 | 2026-11-06 | Planned
HB-B07 | 32.9 | 2026-09-13 | 2026-11-12 | Planned
HB-B08 | 33.1 | 2026-09-21 | 2026-11-17 | Planned
HB-B09 | 33.7 | 2026-09-29 | 2026-11-22 | Planned
HB-B10 | 33.9 | 2026-10-07 | 2026-11-29 | Planned
HB-B11 | 34.5 | 2026-10-15 | 2026-12-04 | Planned
HB-B12 | 35 | 2026-10-23 | 2026-12-10 | Planned
HB-B13 | 35.2 | 2026-10-31 | 2026-12-15 | Planned
HB-C01 | 31.8 | 2026-11-08 | 2026-12-21 | Planned
HB-C02 | 32.3 | 2026-11-16 | 2026-12-27 | Planned
HB-C03 | 32.4 | 2026-11-24 | 2027-01-01 | Planned
HB-C04 | 32.9 | 2026-12-01 | 2027-01-07 | Planned
HB-C05 | 33 | 2026-12-09 | 2027-01-11 | Planned
HB-C06 | 33.6 | 2026-12-17 | 2027-01-16 | Planned
HB-C07 | 34.1 | 2026-12-25 | 2027-01-22 | Planned
HB-C08 | 34.2 | 2027-01-02 | 2027-01-28 | Planned
HB-C09 | 34.7 | 2027-01-10 | 2027-02-03 | Planned
HB-C10 | 34.8 | 2027-01-18 | 2027-02-09 | Planned
HB-C11 | 35.4 | 2027-01-26 | 2027-02-15 | Planned
HB-C12 | 35.9 | 2027-02-03 | 2027-02-19 | Planned
HB-C13 | 36 | 2027-02-11 | 2027-02-26 | Planned