Steering Committee Minutes – 24 June 2026

Harrow Bay Offshore Wind

Elena Márquez  ·  27 June 2026  ·  HB-PM-MIN-SC06

| Meeting | Date | Location |
| --- | --- | --- |
| Harrow Bay Steering Committee No. 6 | 24 June 2026 | Hamburg HQ, Am Sandtorkai 41 / Teams |

Present: Dr. Amara Okafor (chair), Jonas Richter, Paul Wagner, Elena Márquez, Sofie Lindqvist, Hannah Weber, Priya Nair, Marcus Bell; Gareth Lewis (minutes)

# Agenda and discussion

## 1. Safety

Hannah Weber presented the investigation of near miss HSE-INC-2026-018 (dropped shackle pin on MV Sea Atlas, 3 June). Root cause: missing split pin on a bow shackle, not detected in pre-use inspection. Eight corrective actions, five closed. The committee asked for the DROPS learning to be shared with all contractors and the Kestrel Ridge team.

## 2. Progress

10 of 40 monopiles installed vs. 12 in the Rev 2 baseline. The deficit stems from weather in May and the 34-hour lifting stand-down. OSS jacket installation planned for 27 June. Elena Márquez expects to recover one pile in August.

## 3. Cost

Marcus Bell reported actual spend of EUR 612 m against a budget of EUR 1,620 m; EAC unchanged at EUR 1,620 m with EUR 46.4 m contingency remaining.

## 4. July restriction

Committee confirmed use of the July piling restriction for planned maintenance of MV Sea Atlas (decision D-010).

# Actions

| # | Action | Owner | Due | Status |
| --- | --- | --- | --- | --- |
| A6.1 | Share DROPS learning from HSE-INC-2026-018 with all contractors | Hannah Weber | 15 Jul 2026 | Closed |
| A6.2 | Present weather downtime statistics vs. charter allowance | Felix Brandt | 29 Jul 2026 | Closed |
| A6.3 | Confirm OSS topside lift windows with Norfab | Mei Tanaka | 29 Jul 2026 | Closed |

Next meeting: 29 July 2026.