Steering Committee Minutes – 29 July 2026

Harrow Bay Offshore Wind

Elena Márquez  ·  01 August 2026  ·  HB-PM-MIN-SC07

| Meeting | Date | Location |
| --- | --- | --- |
| Harrow Bay Steering Committee No. 7 | 29 July 2026 | Teams |

Present: Dr. Amara Okafor (chair), Jonas Richter, Paul Wagner, Elena Márquez, Sofie Lindqvist, Priya Nair, Marcus Bell; Mei Tanaka (item 2); Gareth Lewis (minutes)

# Agenda and discussion

## 1. Safety

No lost time injuries. One medical treatment case on 8 July in port (finger laceration). LTIF remains 0.

## 2. Export cable 2 – HB-RISK-017

Mei Tanaka reported the factory test failure notified by Severn Subsea Cables on 21 July: partial discharge in a factory joint during the high-voltage test. Severn expects to re-manufacture a 9 km section; indicative delay 8 weeks. Priya Nair confirmed that the reservation of rights letter was issued on 24 July and that delay LDs of EUR 85,000 per day apply after the 21-day grace period, capped at 10 % of the contract price.

## 3. Options

Three options were discussed: (A) wait for cable 2 and keep sequence, (B) resequence cable lay with export cable 1 first and array strings A/B earlier, (C) source a second cable lay vessel. The committee asked for option B to be worked up for decision in August.

## 4. Progress

Seasonal piling restriction until 31 July; MV Sea Atlas maintenance completed on schedule. 10 of 40 monopiles installed.

# Actions

| # | Action | Owner | Due | Status |
| --- | --- | --- | --- | --- |
| A7.1 | Work up cable lay resequencing option B incl. cost and vessel availability | Mei Tanaka | 26 Aug 2026 | Closed |
| A7.2 | Brief the Executive Board on HB-RISK-017 | Elena Márquez | 5 Aug 2026 | Closed |
| A7.3 | Inform Hanseatic Infrastructure Bank (LTA) of the cable delay | Marcus Bell | 7 Aug 2026 | Closed |

Next meeting: 02 September 2026.