Steering Committee Minutes – 26 August 2026

Harrow Bay Offshore Wind

Elena Márquez  ·  29 August 2026  ·  HB-PM-MIN-SC08

| Meeting | Date | Location |
| --- | --- | --- |
| Harrow Bay Steering Committee No. 8 | 26 August 2026 | Hamburg HQ, Am Sandtorkai 41 / Teams |

Present: Dr. Amara Okafor (chair), Jonas Richter, Paul Wagner, Elena Márquez, Sofie Lindqvist, Hannah Weber, Priya Nair, Marcus Bell; Gareth Lewis (minutes)

# Agenda and discussion

## 1. Milestone

The committee congratulated the team on the safe installation of the offshore substation topside on 19 August.

## 2. Export cable 2

Severn's recovery programme (14 August) confirms delivery of export cable 2 on 12 March 2027. With resequencing option B, first power on 30 September 2027 is maintained via export cable 1; full export capacity follows with cable 2 energisation by 30 September 2027. Estimated additional cost EUR 6.8 m (CO-010), to be offset against LDs. Decision D-013: option B approved.

## 3. Progress

12 of 40 monopiles installed vs. 14 planned. Weather downtime in August already 103 h against the monthly charter allowance of 75 h.

## 4. Cost

EAC EUR 1,620 m; contingency remaining EUR 33.7 m after CO-009 (weather standby) and provisional CO-010.

# Actions

| # | Action | Owner | Due | Status |
| --- | --- | --- | --- | --- |
| A8.1 | Negotiate CO-010 with Severn, LD offset | Priya Nair | 30 Sep 2026 | Open |
| A8.2 | Prepare monopile recovery plan incl. charter option 2 | Felix Brandt | 23 Sep 2026 | Closed |
| A8.3 | Update lender model and inform LTA | Marcus Bell | 15 Sep 2026 | Closed |

Next meeting: 30 September 2026.