Steering Committee Minutes – 23 September 2026

Harrow Bay Offshore Wind

Elena Márquez  ·  26 September 2026  ·  HB-PM-MIN-SC09

| Meeting | Date | Location |
| --- | --- | --- |
| Harrow Bay Steering Committee No. 9 | 23 September 2026 | Hamburg HQ, Am Sandtorkai 41 / Teams |

Present: Dr. Amara Okafor (chair), Jonas Richter, Paul Wagner, Elena Márquez, Sofie Lindqvist, Hannah Weber, Priya Nair, Marcus Bell; Felix Brandt (item 2); Gareth Lewis (minutes). Held at Hamburg HQ during the North Sea Energy Summit.

# Agenda and discussion

## 1. Safety

No lost time injuries since construction start (412,000 man-hours). Hannah Weber noted increasing fatigue risk with 24/7 operations; fatigue management plan required before the switch.

## 2. Monopile recovery plan

Felix Brandt presented the recovery plan: 13 of 40 monopiles installed (HB-A14 pitched, waiting on weather), 3 behind baseline. Measures: (1) exercise charter option 2 under WE-CON-2025-040 (+45 days, EUR 2.25 m, CO-011); (2) 24/7 piling outside the night-time restriction areas; (3) load-out of four instead of three piles per trip for string B. Forecast for last monopile 26 February 2027, two weeks after baseline, without impact on first turbine installation. Decisions D-015 and D-016 approved.

## 3. Export cable 2 – HB-RISK-017

Resequenced lay programme issued. CO-010 under negotiation; Severn has accepted that LDs apply but disputes the start date of the grace period. Risk remains red.

## 4. Cost

Actual spend EUR 790 m (48.8 %). EAC EUR 1,620 m; contingency remaining EUR 31.4 m after CO-011. Potential LD recovery of EUR 4.2 m not yet included.

# Actions

| # | Action | Owner | Due | Status |
| --- | --- | --- | --- | --- |
| A9.1 | Fatigue management plan for 24/7 piling | Hannah Weber | 3 Oct 2026 | Open |
| A9.2 | Issue CO-011 and update charter schedule | Felix Brandt | 30 Sep 2026 | Closed |
| A9.3 | Escalation meeting Severn CEO level if CO-010 not agreed | Elena Márquez | 15 Oct 2026 | Open |
| A9.4 | Q3 lender report incl. recovery plan | Marcus Bell | 15 Oct 2026 | Open |

Next meeting: 21 October 2026.