## Daily log
Date | Location | Main activity | Operations (h) | Waiting on weather (h) | Transit / port (h) | Hs max (m) | Wind max (m/s) | POB | Fuel (m³) | Remarks
2026-07-01 | Harrow Bay site | TP installation / bolt tensioning (no piling – seasonal restriction) | 22 | 2 | 0 | 1.1 | 6.3 | 102 | 22
2026-07-02 | HB-A10 | Transition piece installation HB-A10 | 23 | 1 | 0 | 1 | 8.1 | 99 | 23.8
2026-07-03 | Harrow Bay site | TP installation / bolt tensioning (no piling – seasonal restriction) | 21 | 3 | 0 | 1 | 7.3 | 95 | 25.3
2026-07-04 | Port of Eastholm | Planned maintenance – crane and legs | 0 | 0 | 24 | 0.9 | 5.2 | 40 | 10.7
2026-07-05 | Port of Eastholm | Planned maintenance – crane and legs | 0 | 2 | 22 | 1.1 | 8.5 | 44 | 9.5
2026-07-06 | Port of Eastholm | Planned maintenance – crane and legs | 0 | 0 | 24 | 0.6 | 5.7 | 38 | 11.5
2026-07-07 | Port of Eastholm | Planned maintenance – crane and legs | 0 | 0 | 24 | 1 | 7.9 | 36 | 9.6
2026-07-08 | Port of Eastholm | Planned maintenance – crane and legs | 0 | 0 | 24 | 1.1 | 6.2 | 45 | 10.3 | Medical treatment case – finger laceration (hammer overhaul)
2026-07-09 | Port of Eastholm | Planned maintenance – crane and legs | 0 | 0 | 24 | 0.6 | 5.2 | 39 | 11.2
2026-07-10 | Port of Eastholm | Planned maintenance – crane and legs | 0 | 0 | 24 | 1 | 5.2 | 40 | 9.8
2026-07-11 | Port of Eastholm | Planned maintenance – crane and legs | 0 | 0 | 24 | 1.1 | 6.3 | 42 | 10.9
2026-07-12 | Port of Eastholm | Planned maintenance – crane and legs | 0 | 0 | 24 | 1 | 7.8 | 40 | 12.5
2026-07-13 | Port of Eastholm | Planned maintenance – crane and legs | 0 | 0 | 24 | 0.8 | 5.5 | 41 | 11.4
2026-07-14 | Port of Eastholm | Planned maintenance – crane and legs | 0 | 0 | 24 | 1.2 | 7.9 | 40 | 10.5
2026-07-15 | Port of Eastholm | Planned maintenance – crane and legs | 0 | 0 | 24 | 0.7 | 6.7 | 43 | 12.9
2026-07-16 | Port of Eastholm | Planned maintenance – crane and legs | 0 | 0 | 24 | 1 | 6.3 | 43 | 12.4
2026-07-17 | Port of Eastholm | Planned maintenance – crane and legs | 0 | 0 | 24 | 0.8 | 6.6 | 42 | 11.8
2026-07-18 | Port of Eastholm | Planned maintenance – crane and legs | 0 | 0 | 24 | 0.7 | 6.3 | 45 | 12
2026-07-19 | Port of Eastholm | Planned maintenance – crane and legs | 0 | 0 | 24 | 0.6 | 6.7 | 37 | 12.7
2026-07-20 | Port of Eastholm | Planned maintenance – crane and legs | 0 | 0 | 24 | 0.6 | 7.4 | 45 | 11.1
2026-07-21 | Port of Eastholm | Planned maintenance – crane and legs | 0 | 0 | 24 | 0.7 | 7.1 | 41 | 11.9
2026-07-22 | Port of Eastholm | Planned maintenance – crane and legs | 0 | 0 | 24 | 0.7 | 5.7 | 40 | 9.2
2026-07-23 | Port of Eastholm | Planned maintenance – crane and legs | 0 | 0 | 24 | 0.8 | 5.7 | 40 | 11.1
2026-07-24 | Port of Eastholm | Planned maintenance – crane and legs | 0 | 0 | 24 | 1 | 6.5 | 44 | 9.2
2026-07-25 | Port of Eastholm | Load-out of monopiles and TPs | 0 | 0 | 24 | 1.1 | 5.3 | 39 | 9.8
2026-07-26 | Port of Eastholm | Load-out of monopiles and TPs | 0 | 0 | 24 | 0.7 | 7.6 | 43 | 10.6
2026-07-27 | Port of Eastholm | Load-out of monopiles and TPs | 0 | 2 | 22 | 1.2 | 7 | 41 | 12.7
2026-07-28 | Port of Eastholm | Load-out of monopiles and TPs | 0 | 1 | 23 | 0.9 | 6.5 | 43 | 13
2026-07-29 | Port of Eastholm | Load-out of monopiles and TPs | 0 | 1 | 23 | 0.8 | 7.1 | 38 | 9.9
2026-07-30 | Port of Eastholm | Load-out of monopiles and TPs | 0 | 0 | 24 | 1 | 7.7 | 39 | 9.7
2026-07-31 | Port of Eastholm | Load-out of monopiles and TPs | 0 | 2 | 22 | 1.2 | 7.5 | 41 | 12.2 | Remobilised; seasonal piling restriction ends

## Summary
Metric | Value
Operational hours
Waiting on weather (h)
Transit / port (h)
Average POB
Fuel consumption (m³)
Monopiles installed | 0
Transition pieces installed | 1