## Daily log
Date | Location | Main activity | Operations (h) | Waiting on weather (h) | Transit / port (h) | Hs max (m) | Wind max (m/s) | POB | Fuel (m³) | Remarks
2026-08-01 | Harrow Bay site | Bolt tensioning / TP works | 24 | 0 | 0 | 0.9 | 5 | 101 | 23.1
2026-08-02 | Harrow Bay site | Bolt tensioning / TP works | 23 | 1 | 0 | 1.1 | 7.8 | 93 | 24.7
2026-08-03 | Harrow Bay site | Bolt tensioning / TP works | 21 | 3 | 0 | 1.3 | 7.4 | 98 | 19.6
2026-08-04 | Harrow Bay site | Bolt tensioning / TP works | 20 | 4 | 0 | 1.2 | 8.6 | 103 | 25.5
2026-08-05 | Harrow Bay site | Bolt tensioning / TP works | 24 | 0 | 0 | 1.1 | 7.3 | 102 | 19.8
2026-08-06 | HB-A11 | Monopile installation HB-A11 | 19 | 5 | 0 | 1.5 | 7.8 | 98 | 26
2026-08-07 | Harrow Bay site | Bolt tensioning / TP works | 24 | 0 | 0 | 0.9 | 6.1 | 90 | 20.2
2026-08-08 | Harrow Bay site | Bolt tensioning / TP works | 19 | 5 | 0 | 1.2 | 10.1 | 100 | 18
2026-08-09 | Harrow Bay site | Bolt tensioning / TP works | 22 | 2 | 0 | 1 | 6.6 | 101 | 19.6
2026-08-10 | Harrow Bay site | Bolt tensioning / TP works | 16 | 8 | 0 | 2 | 8.8 | 101 | 18.2
2026-08-11 | HB-A11 | Waiting on weather | 8 | 16 | 0 | 2.5 | 14.5 | 90 | 26.4
2026-08-12 | Harrow Bay site | Bolt tensioning / TP works | 15 | 9 | 0 | 1.6 | 10.6 | 102 | 25.4
2026-08-13 | Harrow Bay site | Bolt tensioning / TP works | 21 | 3 | 0 | 1.4 | 6.4 | 88 | 19.8
2026-08-14 | Harrow Bay site | Bolt tensioning / TP works | 24 | 0 | 0 | 1 | 6 | 101 | 25.4
2026-08-15 | Harrow Bay site | Bolt tensioning / TP works | 18 | 6 | 0 | 1.7 | 9.1 | 97 | 23.8
2026-08-16 | Harrow Bay site | Bolt tensioning / TP works | 20 | 4 | 0 | 1.1 | 7.3 | 104 | 23.6
2026-08-17 | Harrow Bay site | Bolt tensioning / TP works | 22 | 2 | 0 | 1.1 | 7.4 | 99 | 24.5
2026-08-18 | Harrow Bay site | Standby outside OSS exclusion zone | 15 | 9 | 0 | 1.8 | 12 | 102 | 19.7
2026-08-19 | Harrow Bay site | Standby outside OSS exclusion zone | 24 | 0 | 0 | 0.8 | 6 | 101 | 18.1 | OSS topside lift completed 11:15
2026-08-20 | Harrow Bay site | Standby outside OSS exclusion zone | 24 | 0 | 0 | 1 | 7.3 | 90 | 25.1
2026-08-21 | Harrow Bay site | Bolt tensioning / TP works | 23 | 1 | 0 | 0.8 | 7.7 | 88 | 18.5
2026-08-22 | Harrow Bay site | Bolt tensioning / TP works | 15 | 9 | 0 | 1.7 | 11.2 | 90 | 22.2
2026-08-23 | HB-A12 | Monopile installation HB-A12 | 24 | 0 | 0 | 0.7 | 5.6 | 96 | 18.5
2026-08-24 | Harrow Bay site | Bolt tensioning / TP works | 21 | 3 | 0 | 1.2 | 6.6 | 93 | 23.1
2026-08-25 | Harrow Bay site | Bolt tensioning / TP works | 21 | 3 | 0 | 1.5 | 6.4 | 96 | 25.4
2026-08-26 | HB-A12 | Transition piece installation HB-A12 | 17 | 7 | 0 | 1.4 | 10.1 | 91 | 26
2026-08-27 | Port of Eastholm | Load-out of monopiles and TPs | 0 | 7 | 17 | 1.5 | 9.7 | 97 | 12.8
2026-08-28 | Port of Eastholm | Load-out of monopiles and TPs | 0 | 5 | 19 | 1.7 | 10 | 100 | 10.3
2026-08-29 | Port of Eastholm | Load-out of monopiles and TPs | 0 | 0 | 24 | 1.1 | 7.7 | 95 | 9.6
2026-08-30 | Harrow Bay site | Bolt tensioning / TP works | 23 | 1 | 0 | 1 | 8.1 | 101 | 18.9
2026-08-31 | Harrow Bay site | Waiting on weather | 8 | 16 | 0 | 2.6 | 13.9 | 99 | 23.8

## Summary
Metric | Value
Operational hours
Waiting on weather (h)
Transit / port (h)
Average POB
Fuel consumption (m³)
Monopiles installed | 2
Transition pieces installed | 2