## Daily log
Date | Location | Main activity | Operations (h) | Waiting on weather (h) | Transit / port (h) | Hs max (m) | Wind max (m/s) | POB | Fuel (m³) | Remarks
2026-09-01 | Harrow Bay site | Bolt tensioning / TP works | 17 | 7 | 0 | 1.6 | 10.6 | 98 | 18.7
2026-09-02 | Harrow Bay site | Bolt tensioning / TP works | 14 | 10 | 0 | 2.3 | 10.8 | 91 | 20.3
2026-09-03 | Harrow Bay site | Waiting on weather | 3 | 21 | 0 | 3.2 | 14.9 | 101 | 21.3
2026-09-04 | Harrow Bay site | Bolt tensioning / TP works | 23 | 1 | 0 | 1.1 | 7.4 | 93 | 18.6
2026-09-05 | Harrow Bay site | Bolt tensioning / TP works | 23 | 1 | 0 | 0.9 | 8.4 | 103 | 22.5
2026-09-06 | Harrow Bay site | Bolt tensioning / TP works | 22 | 2 | 0 | 0.8 | 8.9 | 98 | 19.5
2026-09-07 | Harrow Bay site | Bolt tensioning / TP works | 22 | 2 | 0 | 1 | 6 | 97 | 23.3
2026-09-08 | Harrow Bay site | Bolt tensioning / TP works | 23 | 1 | 0 | 1.2 | 7.1 | 91 | 22.8
2026-09-09 | Harrow Bay site | Bolt tensioning / TP works | 24 | 0 | 0 | 0.8 | 7.5 | 88 | 19.2
2026-09-10 | Harrow Bay site | Bolt tensioning / TP works | 11 | 13 | 0 | 2.6 | 11 | 94 | 21.6
2026-09-11 | HB-A13 | Monopile installation HB-A13 | 23 | 1 | 0 | 0.8 | 6.8 | 93 | 18.2
2026-09-12 | Harrow Bay site | Bolt tensioning / TP works | 24 | 0 | 0 | 1.1 | 7.6 | 90 | 18.3
2026-09-13 | Harrow Bay site | Waiting on weather | 8 | 16 | 0 | 2.6 | 13.3 | 94 | 26.5
2026-09-14 | HB-A13 | Transition piece installation HB-A13 | 14 | 10 | 0 | 2.1 | 10.4 | 103 | 20.1
2026-09-15 | Harrow Bay site | Bolt tensioning / TP works | 12 | 12 | 0 | 2.4 | 11.3 | 94 | 22.9
2026-09-16 | Harrow Bay site | Bolt tensioning / TP works | 10 | 14 | 0 | 2.5 | 13.3 | 99 | 19.8
2026-09-17 | Harrow Bay site | Bolt tensioning / TP works | 11 | 13 | 0 | 2.6 | 12.7 | 103 | 25
2026-09-18 | Harrow Bay site | Bolt tensioning / TP works | 18 | 6 | 0 | 1.7 | 9.3 | 102 | 25.8
2026-09-19 | HB-A14 | Standby at HB-A14, preloaded | 19 | 5 | 0 | 1.4 | 8.8 | 90 | 20.6
2026-09-20 | HB-A14 | Standby at HB-A14, preloaded | 13 | 11 | 0 | 2.4 | 11.5 | 103 | 20.3
2026-09-21 | HB-A14 | Standby at HB-A14, preloaded | 19 | 5 | 0 | 1.4 | 9.9 | 88 | 19
2026-09-22 | HB-A14 | Waiting on weather | 4 | 20 | 0 | 3 | 16.7 | 94 | 24.7
2026-09-23 | HB-A14 | Standby at HB-A14, preloaded | 22 | 2 | 0 | 1.4 | 6.2 | 92 | 24.2
2026-09-24 | HB-A14 | Standby at HB-A14, preloaded | 13 | 11 | 0 | 2.1 | 11 | 96 | 23.1
2026-09-25 | HB-A14 | Standby at HB-A14, preloaded | 24 | 0 | 0 | 1.2 | 7.7 | 103 | 20.9
2026-09-26 | HB-A14 | Waiting on weather | 3 | 21 | 0 | 3.5 | 16.8 | 103 | 24.8 | HB-A14 pitched in gripper; driving postponed – forecast Hs 2.8 m
2026-09-27 | HB-A14 | Standby at HB-A14, preloaded | 19 | 5 | 0 | 1.6 | 8.3 | 95 | 22
2026-09-28 | HB-A14 | Standby at HB-A14, preloaded | 24 | 0 | 0 | 1.1 | 7 | 102 | 20
2026-09-29 | HB-A14 | Standby at HB-A14, preloaded | 24 | 0 | 0 | 1 | 7.3 | 104 | 24.4
2026-09-30 | HB-A14 | Monopile installation HB-A14 | 24 | 0 | 0 | 0.9 | 7.6 | 88 | 20.9

## Summary
Metric | Value
Operational hours
Waiting on weather (h)
Transit / port (h)
Average POB
Fuel consumption (m³)
Monopiles installed | 2
Transition pieces installed | 1