## Change orders
CO no. | Contract | Description | Date | Value (EUR m) | Status
CO-001 | WE-CON-2025-027 | Additional anode cages on TPs for HB-B and HB-C strings (corrosion design update) | 2025-12-04 | 1.2 | Approved
CO-002 | WE-CON-2025-031 | Extended burial depth 1.5 m to 2.0 m in fishing grounds KP 12–KP 19 | 2026-01-21 | 0 | Approved – cost neutral
CO-003 | WE-CON-2025-027 | Boat landing redesign for HTS-12 service vessel fendering | 2026-02-27 | 1.65 | Approved
CO-004 | WE-CON-2025-035 | Additional 66 kV switchgear bay for future expansion | 2026-03-10 | 2.4 | Approved
CO-005 | WE-CON-2025-040 | Bubble curtain support vessel – extended scope for second hose ring | 2026-04-02 | 0.92 | Approved
CO-006 | WE-CON-2025-027 | Coating repair procedure and quay inspection (batch 3) | 2026-05-15 | 0.18 | Approved
CO-007 | WE-CON-2025-027 | Increased pile wall thickness at HB-C10 to HB-C13 after geotechnical update | 2026-06-11 | 0.57 | Approved
CO-008 | WE-CON-2025-035 | Helideck lighting upgrade to CAP 437 edition 9 | 2026-06-30 | 0.8 | Approved
CO-009 | WE-CON-2025-040 | Weather standby above contractual allowance (April–August) | 2026-08-31 | 2.33 | Approved
CO-010 | WE-CON-2025-031 | Resequencing of cable lay campaign following export cable 2 delay | 2026-09-08 | 6.8 | Under negotiation – LD offset reserved
CO-011 | WE-CON-2025-040 | Exercise of charter option 2 (+45 days) | 2026-09-24 | 2.25 | Approved by SteerCo 2026-09-23
CO-012 | WE-CON-2025-035 | Topside lift: additional sea-fastening removal shift | 2026-08-27 | 0 | Rejected
Total |  | approved and pending

## By contract
Contract | Approved (EUR m) | Pending (EUR m)
WE-CON-2025-027 | 3.6 | 0
WE-CON-2025-031 | 0 | 6.8
WE-CON-2025-035 | 3.2 | 0
WE-CON-2025-040 | 5.5 | 0