Contract Summary WE-CON-2025-022

Halden Turbine Systems A/S

Priya Nair  ·  15 June 2026  ·  WE-CON-2025-022

| Field | Details |
| --- | --- |
| Contract no. | WE-CON-2025-022 |
| Counterparty | Halden Turbine Systems A/S |
| Signed | 2025-06-30 |
| Form | FIDIC Yellow Book (2017), amended |
| Weyland contract owner | Elena Márquez |
| Legal | Priya Nair / Lukas Meyer |

# Scope

Supply, installation and commissioning of 40 × HTS-12 12 MW turbines, 5-year service and availability warranty.

# Price

EUR 575.0 m fixed price (40 × HTS-12 incl. installation and commissioning), 5-year service agreement priced separately at EUR 9.8 m p.a.

# Payment milestones

| Milestone | Share / timing |
| --- | --- |
| Down payment at signature | 10 % |
| Start of nacelle production | 20 % |
| Delivery to Port of Eastholm (per turbine) | 40 % |
| Mechanical completion (per turbine) | 20 % |
| Taking over certificate | 10 % |

# Liquidated damages

Delay LDs EUR 45,000 per turbine per day after the guaranteed delivery date; cap 12 % of contract price. Performance LDs on power curve below 97 %.

# Warranty

5-year defects liability; 97 % time-based availability guarantee during the service period.

# Key points for the project team

Turbine delivery: Jan 2027 – Dec 2027, 4 turbines per month

Installation by Halden with its own installation vessel from 1 March 2027

Interface to transition piece flange per HB-IF-001

Performance security: 10 % bank guarantee (Danske-rated bank)

This is a summary for project use only. In case of doubt the signed contract in the Legal & Contracts space prevails.