Contract Summary WE-CON-2025-031

Severn Subsea Cables Ltd

Priya Nair  ·  28 September 2026  ·  WE-CON-2025-031

| Field | Details |
| --- | --- |
| Contract no. | WE-CON-2025-031 |
| Counterparty | Severn Subsea Cables Ltd |
| Signed | 2025-09-15 |
| Form | FIDIC Yellow Book (2017), amended |
| Weyland contract owner | Mei Tanaka |
| Legal | Priya Nair / Lukas Meyer |

# Scope

Design, manufacture, testing, installation and burial of 2 × 220 kV export cables (62 km each) and ~95 km of 66 kV array cables.

# Price

EUR 232.0 m fixed price for supply and installation; CO-010 (EUR 6.8 m resequencing) under negotiation.

# Payment milestones

| Milestone | Share / timing |
| --- | --- |
| Advance payment | 10 % |
| Design approval | 5 % |
| Factory acceptance test (per cable) | 35 % |
| Load-out | 20 % |
| Installation and burial complete | 20 % |
| Post-installation test | 10 % |

# Liquidated damages

Delay LDs EUR 85,000 per day after a 21-day grace period from the guaranteed delivery date; cap 10 % of contract price (EUR 23.2 m).

# Warranty

5-year defects liability on cable and accessories; 2-year on installation works.

# Key points for the project team

Export cable 1: manufactured, FAT passed 2 June 2026, delivery 11 December 2026

Export cable 2: factory test failure 21 July 2026 – 9 km re-manufacture, delivery 12 March 2027 (HB-RISK-017)

Array cables: 95 km, manufacture from November 2026

Lay campaign resequenced per SteerCo decision D-013

This is a summary for project use only. In case of doubt the signed contract in the Legal & Contracts space prevails.