## Summary
Package | Contract | Budget (EUR m) | Committed (EUR m) | Actual to date (EUR m) | EAC (EUR m) | Variance EAC vs. budget | % spent of EAC
Wind turbines (supply & installation) | WE-CON-2025-022 | 575 | 575 | 172.5 | 575
Monopiles & transition pieces | WE-CON-2025-027 | 268 | 271.6 | 181.2 | 271.6
Export & array cables (supply & installation) | WE-CON-2025-031 | 232 | 232 | 104.4 | 238.8
Offshore substation HB-OSS (EPCI) | WE-CON-2025-035 | 196 | 199.2 | 158.8 | 199.2
Foundation installation vessel MV Sea Atlas | WE-CON-2025-040 | 88 | 93.5 | 41.6 | 93.5
Onshore substation & grid connection | WE-CON-2025-044 | 61 | 58.7 | 33.9 | 61
Port, logistics & marine services | various | 34 | 27.4 | 15.2 | 35.8
Development & consents | – | 38 | 38 | 38 | 38
Owner's costs & project management | – | 52 | 31 | 29.7 | 54.3
Insurance (CAR / marine) | – | 21 | 21.4 | 14.6 | 21.4
Contingency | – | 55 | 0 | 0 | 31.4
Total

## Monthly trend
Month | Actual cumulative (EUR m) | Budget cumulative (EUR m) | Variance (EUR m)
2026-01 | 402.6 | 405
2026-02 | 438.1 | 441
2026-03 | 497.3 | 503
2026-04 | 541.8 | 552
2026-05 | 579.4 | 596
2026-06 | 612 | 634
2026-07 | 664.5 | 676
2026-08 | 731.2 | 744
2026-09 | 789.9 | 812

## Contingency
Item | EUR m
Contingency at FID | 55
CO-001 Additional anode cages on TPs for HB-B and HB-C strings (cor | -1.2
CO-003 Boat landing redesign for HTS-12 service vessel fendering | -1.65
CO-004 Additional 66 kV switchgear bay for future expansion | -2.4
CO-005 Bubble curtain support vessel – extended scope for second ho | -0.92
CO-006 Coating repair procedure and quay inspection (batch 3) | -0.18
CO-007 Increased pile wall thickness at HB-C10 to HB-C13 after geot | -0.57
CO-008 Helideck lighting upgrade to CAP 437 edition 9 | -0.8
CO-009 Weather standby above contractual allowance (April–August) | -2.33
CO-010 Resequencing of cable lay campaign following export cable 2 | -6.8
CO-011 Exercise of charter option 2 (+45 days) | -2.25
Port & logistics re-forecast | -1.8
Owner's costs re-forecast (24/7 operations) | -2.3
Insurance premium adjustment | -0.4
Contingency remaining