Quarterly Construction Report Q3 2026

Harrow Bay Offshore Wind · for Hanseatic Infrastructure Bank and the lender group

Marcus Bell  ·  02 October 2026  ·  HB-FIN-LR-2026-Q3

DRAFT – for review by Elena Márquez and Jonas Richter before submission on 15 October.

# 1. Executive summary

By 30 September 2026, 13 of 40 monopiles were installed (HB-A14 completed on 30 September, reported after period end), against 16 in the baseline. The offshore substation topside was installed on 19 August. The Steering Committee approved a recovery plan on 23 September (charter option 2, 24/7 piling). Forecast for the last monopile is 26 February 2027; first power remains 30 September 2027.

# 2. Construction progress

| Workstream | Status |
| --- | --- |
| Foundations | 13/40 monopiles installed |
| Offshore substation | Topside installed 19 Aug |
| Export cables | Cable 2 delayed – delivery 12 Mar 2027 |
| Turbines | Manufacturing started in Aarhus |
| Onshore substation | Civil works 62 %, transformers ordered |

# 3. Cost and financing

Actual spend to 30 September 2026: EUR 789.9 m (48.8 % of EAC). EAC remains EUR 1,620 m; contingency remaining EUR 31.4 m. Potential recovery of liquidated damages from Severn Subsea Cables (est. EUR 4.2 m) is not included.

Capex development

| Drawdown | Date | Amount (EUR m) |
| --- | --- | --- |
| DR-06 | 15 Jul 2026 | 48.1 |
| DR-07 | 17 Aug 2026 | 62.9 |
| DR-08 | 15 Sep 2026 | 57.3 |

# 4. Key risks

| ID | Risk | Rating | Mitigation |
| --- | --- | --- | --- |
| HB-RISK-017 | Export cable 2 delay (Severn) | High | Resequenced cable lay; LDs under WE-CON-2025-031 |
| HB-RISK-029 | Monopile campaign into winter | High | Charter option 2, 24/7 piling |
| HB-RISK-030 | Turbine installation start | High | Install string A first |

# 5. HSE and environment

Zero lost time injuries. Noise monitoring: one exceedance at HB-A04 (April), all other piles compliant. Marine mammal and seabird monitoring by Marlow Ecology in line with consent conditions.

# 6. Compliance with finance documents

No event of default. All information undertakings met. The Lenders' Technical Adviser visited the Port of Eastholm and MV Sea Atlas on 8 September 2026 and confirmed the recovery plan as reasonable.