## Permits
Asset / project | Permit / consent | Authority | Reference | Issued | Expiry / review | Key conditions | Conditions (no.) | Open actions | Owner
Harrow Bay | Development consent | Secretary of State (UK) | HB-DCO-2023 | 2023-11-20 | Construction start ≤ 2028 | Design envelope, monitoring | 46 | 3 | Charlotte Dubois
Harrow Bay | Marine licence (generation assets) | Marine regulator | HB-ML-01 | 2023-11-20 | Operation + decommissioning | Piling noise, seabirds, harbour porpoise, notices to mariners | 38 | 4 | Clara Neumann
Harrow Bay | Marine licence (transmission assets) | Marine regulator | HB-ML-02 | 2023-11-20 | Operation + decommissioning | Cable burial, sandwave clearance | 29 | 2 | Clara Neumann
Harrow Bay | European protected species licence – harbour porpoise | Nature conservation body | EPS-HB-2026-07 | 2026-03-02 | 2027-12-31 | Bubble curtain, MMO/PAM, soft start | 12 | 0 | Clara Neumann
Harrow Bay | Onshore construction – environmental permit for dewatering | Environment agency | EPR/HB/0193 | 2025-10-14 | 2026-12-31 | Discharge quality monitoring | 9 | 0 | Clara Neumann
Kestrel Ridge | Planning consent | Local planning authority | KR-PC-2019 | 2020-02-11 | Operational life 30 years | Noise, shadow flicker, ice, ornithology | 31 | 1 | David Chen
Kestrel Ridge | Waste carrier registration (site vehicles) | Environment agency | CBDL-48211 | 2024-01-08 | 2027-01-08 | – | 0 | 0 | Ben Okoye
Skerrow Moor | Planning consent | Local planning authority | SM-PC-2012 | 2013-05-02 | 2041 | Noise, birds | 24 | 0 | Site manager
Altmark | BImSchG permit | Landesamt | AM-BImSchG-2018 | 2018-10-09 | Operational life | Bat curtailment, crane protection zone | 49 | 1 | Site manager
Emsland | BImSchG permit | Landkreis | EL-BImSchG-2016 | 2016-12-01 | Operational life | Noise night mode, shadow flicker | 44 | 0 | Site manager
Nordheide | BImSchG permit | Landkreis | NH-BImSchG-2015 | 2015-08-19 | Operational life | Noise night mode, bat curtailment Apr–Oct | 52 | 1 | Site manager
Wesermarsch | BImSchG permit | Landkreis | WM-BImSchG-2013 | 2013-06-03 | Operational life | Bat curtailment, shadow flicker | 47 | 0 | Site manager
Ostholstein | BImSchG permit | Landesamt | OH-BImSchG-2019 | 2019-11-21 | Operational life | Red kite protection measures | 58 | 2 | Site manager
Thy Vest | Environmental approval (VVM) | Kommune | TV-VVM-2016 | 2016-09-15 | Operational life | Noise, birds | 21 | 0 | Site manager
Uckermark Solar | Building permit + landscape plan | Landkreis | UM-BP-2019 | 2019-07-30 | Operational life | Sheep grazing, hedgerows | 18 | 0 | Site manager
Millbrook (planned) | Planning application | Millbrook District Council | MDC/2026/0412 | submitted 2026-06-18 | Decision expected Q1 2027 | BNG 20 %, skylark plots | 0 | 0 | Liam McAllister