## Register 2026
Incident no. | Date | Site / project | Category | Severity (actual) | Potential | Description | Reportable | Investigation lead | Status | Linked reference
HSE-INC-2026-001 | 2026-01-09 | Altmark | First aid | Minor | Low | Insect sting during vegetation work | No | Site manager | Closed
HSE-INC-2026-002 | 2026-01-14 | Kestrel Ridge | Environmental / asset damage | Minor | Low | T-07 gearbox ISS bearing failure, ~4 l oil contained in nacelle drip tray, no release to ground | No | Ben Okoye | Closed | KR-INC-2026-003
HSE-INC-2026-003 | 2026-01-21 | Kestrel Ridge | Property damage | Minor | Low | Company van struck gate post at site entrance | No | Ben Okoye | Closed
HSE-INC-2026-004 | 2026-01-28 | Hamburg office | Near miss | None | Medium | Vehicle reversing on site without banksman | No | Ben Okoye | Closed
HSE-INC-2026-005 | 2026-02-04 | Kestrel Ridge | Near miss | None | Medium | Crane outrigger mat settled 40 mm in thawing ground during T-07 gearbox lift – lift paused, mats re-laid | No | Hannah Weber | Closed | KR-INC-2026-003
HSE-INC-2026-006 | 2026-02-19 | Uckermark Solar | Injury – MTC | Minor | Low | Cut to hand when opening combiner box, 3 stitches | No | Site manager | Closed
HSE-INC-2026-007 | 2026-03-19 | Altmark | Injury – LTI | Moderate | Medium | Contractor technician fractured ankle stepping off the tower ladder rest platform, 23 days lost | Yes – Unfallanzeige to BG | Hannah Weber | Closed
HSE-INC-2026-008 | 2026-03-24 | Harrow Bay – MV Sea Atlas | Near miss | None | Medium | Technician started climb without second person on site | No | Yusuf Demir | Closed
HSE-INC-2026-009 | 2026-03-29 | Hamburg office | Near miss | None | Medium | Crew transfer in sea state above limit started – aborted by skipper | No | Yusuf Demir | Closed
HSE-INC-2026-010 | 2026-04-04 | Altmark | Property damage | Minor | Low | Company van struck gate post at site entrance | No | Site manager | Closed
HSE-INC-2026-011 | 2026-04-09 | Harrow Bay – onshore substation | Injury – MTC | Minor | Low | Foreign body in eye while grinding, removed at hospital | No | Yusuf Demir | Closed
HSE-INC-2026-012 | 2026-04-19 | Harrow Bay – MV Sea Atlas | Near miss | None | Medium | Technician started climb without second person on site | No | Site manager | Closed
HSE-INC-2026-013 | 2026-04-28 | Uckermark Solar | Environmental | Minor | Low | Small diesel spill at refuelling point, cleaned up with spill kit | No | Yusuf Demir | Closed
HSE-INC-2026-014 | 2026-05-08 | Harrow Bay – MV Sea Atlas | Injury – RWC | Moderate | Medium | Knee injury stepping off gangway, 5 days restricted work | No | Yusuf Demir | Closed
HSE-INC-2026-015 | 2026-05-14 | Uckermark Solar | Near miss | None | Medium | Technician started climb without second person on site | No | Site manager | Closed
HSE-INC-2026-016 | 2026-05-21 | Harrow Bay – MV Sea Atlas | Near miss | None | Medium | Vehicle reversing on site without banksman | No | Site manager | Closed
HSE-INC-2026-017 | 2026-05-28 | Thy Vest | Near miss | None | Medium | Vehicle reversing on site without banksman | No | Ben Okoye | Closed
HSE-INC-2026-018 | 2026-06-03 | Harrow Bay – MV Sea Atlas | Near miss – dropped object (HiPo) | None | High (fatality) | 2.3 kg ratchet spanner fell ~22 m from pile gripper frame, landed 2.5 m from deck foreman; no injuries | No (not RIDDOR-reportable); lender notified | Yusuf Demir | Closed – actions tracked | SA-2026-04
HSE-INC-2026-019 | 2026-06-13 | Kestrel Ridge | Property damage | Minor | Low | Company van struck gate post at site entrance | No | Ben Okoye | Closed
HSE-INC-2026-020 | 2026-06-22 | Harrow Bay – Port of Eastholm | Injury – MTC | Minor | Low | Back strain during sea-fastening removal | No | Yusuf Demir | Closed
HSE-INC-2026-021 | 2026-06-26 | Wesermarsch | Environmental | Minor | Low | Small diesel spill at refuelling point, cleaned up with spill kit | No | Site manager | Closed
HSE-INC-2026-022 | 2026-06-30 | Harrow Bay – MV Sea Atlas | Near miss | None | Low | Unsecured load shifted on flatbed trailer | No | Yusuf Demir | Closed
HSE-INC-2026-023 | 2026-07-04 | Harrow Bay – MV Sea Atlas | Near miss | None | Medium | Crew transfer in sea state above limit started – aborted by skipper | No | Ben Okoye | Closed
HSE-INC-2026-024 | 2026-07-08 | Harrow Bay – MV Sea Atlas | Injury – RWC | Moderate | Medium | Finger fracture, hand caught between pile handling tool and guide, 12 days restricted duties | Yes – RIDDOR (over-7-day) | Yusuf Demir | Closed
HSE-INC-2026-025 | 2026-07-20 | Hamburg office | Near miss | None | Medium | Technician started climb without second person on site | No | Site manager | Closed
HSE-INC-2026-026 | 2026-07-31 | Skerrow Moor | Near miss | None | Medium | Gas bottle stored without restraint in workshop | No | Site manager | Closed
HSE-INC-2026-027 | 2026-08-12 | Harrow Bay – transition piece | Injury – MTC | Minor | Low | Laceration to shin on platform grating | No | Yusuf Demir | Closed
HSE-INC-2026-028 | 2026-08-19 | Harrow Bay – MV Sea Atlas | Environmental | Minor | Low | Hydraulic oil leak (approx. 15 l) on jack-up leg, contained on deck | Reported to marine regulator | Clara Neumann | Closed
HSE-INC-2026-029 | 2026-08-26 | Harrow Bay – MV Sea Atlas | Near miss | None | Medium | Crew transfer in sea state above limit started – aborted by skipper | No | Ben Okoye | Closed
HSE-INC-2026-030 | 2026-09-02 | Skerrow Moor | Near miss | None | Medium | Technician started climb without second person on site | No | Site manager | Open
HSE-INC-2026-031 | 2026-09-09 | Uckermark Solar | Near miss | None | Medium | Crew transfer in sea state above limit started – aborted by skipper | No | Ben Okoye | Open
HSE-INC-2026-032 | 2026-09-16 | Harrow Bay – MV Sea Atlas | First aid | Minor | Low | Insect sting during vegetation work | No | Site manager | Open
HSE-INC-2026-033 | 2026-09-23 | Nordheide | Near miss | None | Medium | Crew transfer in sea state above limit started – aborted by skipper | No | Site manager | Open

## Notes
Scope
Injuries, environmental incidents, property damage, security events and near misses with medium or high potential. Low-potential near misses and safety observations are recorded in the reporting app and counted in the HSE statistics.