## Turbines 2026
Turbine | Landowner | Annual service planned | Annual service actual | Status | Blade inspection (drone) | Lift LOLER (6-monthly) | Oil sample (3-monthly) last | Notes
T-01 | Hartside Farm | 2026-04-10 | 2026-04-13 | Completed | 2026-08-04 | 2026-03 / 2026-09 | 2026-09-11
T-02 | Hartside Farm | 2026-04-09 | 2026-04-15 | Completed | 2026-08-05 | 2026-03 / 2026-09 | 2026-09-12
T-03 | Hartside Farm | 2026-04-21 | 2026-04-21 | Completed | 2026-08-06 | 2026-03 / 2026-09 | 2026-09-13
T-04 | Hartside Farm | 2026-05-01 | 2026-05-04 | Completed | 2026-08-07 | 2026-03 / 2026-09 | 2026-07-14 | Fe trend up – resample by 2026-07-15
T-05 | Hartside Farm | 2026-04-30 | 2026-05-06 | Completed | 2026-08-08 | 2026-03 / 2026-09 | 2026-09-15
T-06 | Hartside Farm | 2026-05-19 | 2026-05-19 | Completed | 2026-08-09 | 2026-03 / 2026-09 | 2026-09-16
T-07 | Craigmuir Estate | 2026-09-19 | 2026-09-22 | Completed | 2026-08-10 | 2026-03 / 2026-09 | 2026-09-17 | New gearbox Feb 2026 (KR-INC-2026-003) – service moved to end of campaign
T-08 | Craigmuir Estate | 2026-05-21 | 2026-05-27 | Completed | 2026-08-11 | 2026-03 / 2026-09 | 2026-09-18
T-09 | Craigmuir Estate | 2026-06-02 | 2026-06-02 | Completed | 2026-08-12 | 2026-03 / 2026-09 | 2026-09-19
T-10 | Craigmuir Estate | 2026-06-06 | 2026-06-09 | Completed | 2026-08-13 | 2026-03 / 2026-09 | 2026-09-20
T-11 | Craigmuir Estate | 2026-06-10 | 2026-06-16 | Completed | 2026-08-14 | 2026-03 / 2026-09 | 2026-09-21
T-12 | Craigmuir Estate | 2026-09-15 | 2026-09-15 | Completed | 2026-08-15 | 2026-03 / 2026-09 | 2026-09-22 | ISS bearing replaced May 2026 – service moved to September
T-13 | Craigmuir Estate | 2026-06-20 | 2026-06-23 | Completed | 2026-08-16 | 2026-03 / 2026-09 | 2026-09-23
T-14 | Low Swinton Farm | 2026-07-01 | 2026-07-07 | Completed | 2026-08-17 | 2026-03 / 2026-09 | 2026-09-24
T-15 | Low Swinton Farm | 2026-07-14 | 2026-07-14 | Completed | 2026-08-18 | 2026-03 / 2026-09 | 2026-09-10
T-16 | Low Swinton Farm | 2026-07-18 | 2026-07-21 | Completed | 2026-08-19 | 2026-03 / 2026-09 | 2026-09-11
T-17 | Low Swinton Farm | 2026-08-05 | 2026-08-11 | Completed | 2026-08-20 | 2026-03 / 2026-09 | 2026-09-12
T-18 | Low Swinton Farm | 2026-08-18 | 2026-08-18 | Completed | 2026-08-21 | 2026-03 / 2026-09 | 2026-09-13

## Maintenance tasks
Task | Interval | Scope | Responsible | Next due | Contract reference
Annual service | 12 months | All turbines | Highline | Apr–Sep 2027 | Schedule 2
Safety equipment check | 6 months | Fall arrest, rescue kits, extinguishers | Highline | 2027-03 | Schedule 2
Service lift thorough examination (LOLER) | 6 months | 18 lifts | Highline / insurer engineer | 2027-03 | Schedule 2
Gearbox oil sampling | 3 months (since Mar 2026) | All gearboxes | Highline | 2026-12 | Change note CN-07
Gearbox endoscope | 12 months + on CMS alert | ISS/HSS bearings | Highline | 2027-02 | Change note CN-07
Blade inspection by drone | 12 months | 54 blades | Weyland (contractor) | 2027-08 | –
Tower flange bolt check (10 %) | 12 months | All towers | Highline | with annual service | Schedule 2
Substation maintenance | 12 months | 33/132 kV transformer, switchgear | HV contractor | 2027-05 | Separate contract
Ice detection function test | Annually before winter | All turbines | Highline | 2026-10-15 | Planning condition 12
Shadow flicker module calendar check | Annually | T-03, T-04, T-15 | Weyland | 2027-03 | Planning condition 15
Aviation lighting check | Monthly | All turbines | Control room (remote) + Highline | monthly | CAA requirement
Access track grading and drainage | Annually + after storms | 14.2 km tracks | Civil contractor | 2027-04 | –