## Register
Risk ID | Category | Description | Likelihood (1-5) | Impact (1-5) | Score | Mitigation | Owner | Status | Last review
MB-RISK-001 | Planning | Planning refusal or committee deferral | 3 | 5 |  | Three consultations, amendment pack Oct 2026, early officer engagement | Liam McAllister | Open | 2026-09-29
MB-RISK-002 | Planning | Objections on construction traffic on Mill Lane | 4 | 3 |  | Haul road from B4127, CTMP condition offered, no HGVs at school times | Liam McAllister | Open | 2026-09-29
MB-RISK-003 | Environment | Skylark mitigation judged insufficient by Natural England | 2 | 4 |  | 46 skylark plots, 5-year monitoring, Marlow Ecology attended consultee meeting | Dr. Rachel Moss | Open | 2026-09-29
MB-RISK-004 | Grid | Planning delay beyond Mar 2027 puts grid date 31 Oct 2028 at risk | 3 | 4 |  | Monthly check-ins with NordGrid; modification application prepared as fallback | Sofie Lindqvist | Open | 2026-09-29
MB-RISK-005 | Commercial | Module price increase before EPC award | 3 | 3 |  | Price validity to 30 Jun 2027 with index mechanism in SunForge offer | Liam McAllister | Open | 2026-09-29
MB-RISK-006 | Commercial | SunForge capacity constraint in 2027/28 | 2 | 3 |  | Reserve bidder Calder Solar kept warm | Liam McAllister | Open | 2026-09-29
MB-RISK-007 | HSE | BESS fire safety concerns delay consent | 3 | 3 |  | Outline Battery Safety Management Plan reviewed with fire and rescue service | Hannah Weber | Open | 2026-09-29
MB-RISK-008 | Land | Cable route easement with third landowner (Brook House) not agreed | 2 | 4 |  | Alternative route via B4127 verge assessed | Priya Nair | Open | 2026-09-29
MB-RISK-009 | Planning | Glare complaint from Mill Lane Cottages residents | 3 | 2 |  | 3 m hedgerow screen + temporary screen; independent study shared | Liam McAllister | Open | 2026-09-29
MB-RISK-010 | Environment | Archaeology finds during construction | 2 | 3 |  | Geophysical survey done; trial trenching condition accepted | Liam McAllister | Open | 2026-09-29
MB-RISK-011 | Grid | NordGrid reinforcement works at Millbrook substation delayed | 2 | 4 |  | Track NordGrid programme quarterly; contractual milestones in offer | Sofie Lindqvist | Open | 2026-09-29
MB-RISK-012 | Community | Community fund governance disputes | 2 | 2 |  | Independent fund administrator; panel ToR agreed with parish council | Tom Berger | Open | 2026-09-29
MB-RISK-013 | Planning | Judicial review after consent | 1 | 5 |  | Robust officer report; legal review of conditions | Priya Nair | Open | 2026-09-29
MB-RISK-014 | Environment | Flood risk queried by Lead Local Flood Authority | 2 | 2 |  | Drainage strategy updated; LLFA no objection 11 Aug 2026 | Sofie Lindqvist | Closed | 2026-09-29
MB-RISK-015 | Commercial | Capex overrun above EUR 78 m | 3 | 3 |  | EUR 4.4 m contingency; P80 estimate EUR 80.1 m | Liam McAllister | Open | 2026-09-29
MB-RISK-016 | Planning | Heritage objection (setting of St Mary's Church) | 2 | 3 |  | Field 7 removed; heritage statement; Historic England no comment | Liam McAllister | Closed | 2026-09-29
MB-RISK-017 | Land | Landowner succession at Ashcombe Farm | 1 | 3 |  | Lease binds successors; registered at Land Registry | Priya Nair | Open | 2026-09-29
MB-RISK-018 | Environment | Badger sett disturbance near hedgerow H12 | 2 | 2 |  | 30 m exclusion zone; licence if required | Dr. Rachel Moss | Open | 2026-09-29

## Heat map
Open risks by likelihood and impact
Impact \ Likelihood | 1 | 2 | 3 | 4 | 5
5 | 1 | 0 | 1 | 0 | 0
4 | 0 | 3 | 1 | 0 | 0
3 | 1 | 2 | 3 | 1 | 0
2 | 0 | 2 | 1 | 0 | 0
1 | 0 | 0 | 0 | 0 | 0