Project Board – Minutes

Millbrook Solar & Storage · 2026-07-28

Liam McAllister  ·  29 July 2026

| Item | Details |
| --- | --- |
| Date | 2026-07-28 |
| Location | Edinburgh office, room Forth / Teams |
| Attendees | Liam McAllister (chair), Sofie Lindqvist, Tom Berger, Charlotte Dubois, Priya Nair, Hannah Weber |
| Apologies | none |

# 1. Actions from the last meeting

All actions from the previous meeting are closed.

# 2. Status

Application validated 2 July; council consultation runs to 6 August.

Highways Authority holding response: wants CTMP detail on Mill Lane passing places.

Three compliant EPC bids received on 10 July.

# 3. Decisions

Commission a swept-path analysis for the B4127 junction.

Hold consultation #3 on 16 September to present amendments.

# 4. Actions

| Owner | Action | Due |
| --- | --- | --- |
| Sofie Lindqvist | Swept-path analysis and CTMP Rev 2 | 2026-08-21 |
| Hannah Weber | Outline Battery Safety Management Plan | 2026-08-28 |
| Tom Berger | Consultation #3 venue and leaflet | 2026-08-21 |

Next meeting: last Tuesday of next month. Minutes taken by Grace Mitchell.