Project Board – Minutes

Millbrook Solar & Storage · 2026-09-29

Liam McAllister  ·  30 September 2026

| Item | Details |
| --- | --- |
| Date | 2026-09-29 |
| Location | Teams |
| Attendees | Liam McAllister (chair), Sofie Lindqvist, Tom Berger, Charlotte Dubois, Priya Nair, Marcus Bell |
| Apologies | Ahmed Rahimi |

# 1. Actions from the last meeting

Two actions closed, one carried forward (see section 4).

# 2. Status

Consultation #3 on 16 September: 187 attendees; 173 responses so far, feedback window closes 30 September.

Support has risen from 42 % (#1) to 53 % (#3); Mill Lane traffic remains the top concern.

Grid: NordGrid confirmed the reinforcement programme at Millbrook substation is on track.

# 3. Decisions

Submit amendment pack (CTMP Rev 2, BSMP, hedgerow condition wording) by 16 October.

Start EPC contract negotiation with SunForge in October.

# 4. Actions

| Owner | Action | Due |
| --- | --- | --- |
| Charlotte Dubois | Amendment pack submission | 2026-10-16 |
| Tom Berger | Consultation #3 feedback report | 2026-10-09 |
| Lukas Meyer | EPC contract first draft to SunForge | 2026-10-30 |

Next meeting: last Tuesday of next month. Minutes taken by Charlotte Dubois.