## Schedule
# | Workstream | Task | Start | Finish | Duration (days) | % complete | Owner
1 | Development | Land lease signed | 2025-07-14 | 2025-11-18 |  | 100% | Priya Nair
2 | Development | Grid connection offer accepted (NGT-OFF-2025-1187) | 2025-09-01 | 2025-12-12 |  | 100% | Ahmed Rahimi
3 | Surveys | Habitat and wintering bird surveys | 2025-10-14 | 2026-02-27 |  | 100% | Marlow Ecology
4 | Surveys | Breeding bird survey (skylark) | 2026-04-16 | 2026-06-26 |  | 100% | Marlow Ecology
5 | Surveys | Geophysical survey (archaeology) | 2026-01-12 | 2026-02-20 |  | 100% | Liam McAllister
6 | Design | Layout Rev A | 2026-01-05 | 2026-02-06 |  | 100% | Sofie Lindqvist
7 | Engagement | Public consultation #1 | 2026-03-11 | 2026-04-01 |  | 100% | Tom Berger
8 | Design | Layout Rev B (post consultation #1) | 2026-03-23 | 2026-04-14 |  | 100% | Sofie Lindqvist
9 | Studies | Glint and glare assessment | 2026-04-06 | 2026-05-29 |  | 100% | Sofie Lindqvist
10 | Studies | LVIA and photomontages | 2026-02-02 | 2026-06-10 |  | 100% | Liam McAllister
11 | Engagement | Public consultation #2 | 2026-05-20 | 2026-06-10 |  | 100% | Tom Berger
12 | Design | Layout Rev C (submission) | 2026-05-18 | 2026-06-05 |  | 100% | Sofie Lindqvist
13 | Planning | Planning application submitted (MDC/2026/0412) | 2026-06-18 | 2026-06-18 |  | 100% | Charlotte Dubois
14 | Planning | Validation and council consultation | 2026-06-19 | 2026-08-06 |  | 100% | Charlotte Dubois
15 | Procurement | EPC tender | 2026-05-22 | 2026-09-08 |  | 100% | Liam McAllister
16 | Engagement | Public consultation #3 (amendments) | 2026-09-16 | 2026-09-30 |  | 100% | Tom Berger
17 | Planning | Amendment pack to council | 2026-09-21 | 2026-10-16 |  | 55% | Charlotte Dubois
18 | Planning | Officer report and committee | 2026-11-02 | 2027-02-17 |  | 0% | Charlotte Dubois
19 | Commercial | EPC contract negotiation | 2026-10-05 | 2027-03-31 |  | 5% | Lukas Meyer
20 | Commercial | Financing and investment decision | 2027-03-01 | 2027-07-30 |  | 0% | Jonas Richter
21 | Construction | Construction (12 months) | 2027-08-02 | 2028-07-31 |  | 0% | SunForge EPC
22 | Grid | NordGrid works and energisation | 2028-03-01 | 2028-10-31 |  | 0% | NordGrid Transmission
23 | Commissioning | Commissioning and COD | 2028-08-01 | 2028-12-15 |  | 0% | Liam McAllister