Monthly Status Report – May 2026

Millbrook Solar & Storage

Liam McAllister  ·  03 June 2026  ·  MB-PM-RPT-202605

| Area | RAG | Comment |
| --- | --- | --- |
| Overall | Green | Consultation #2 on 20 May drew 212 attendees and 202 responses. |
| Cost | Green | Development spend EUR 1.88 m of EUR 3.10 m budget (61 %) |
| Schedule | Amber | Planning decision Q1 2027 – on track |
| Stakeholders | Green | Consultations held: 2 of 3 |

# Summary

Consultation #2 on 20 May drew 212 attendees and 202 responses. Layout Rev C (85 MWp) was frozen for submission and the EPC tender was issued on 22 May.

# Key figures

| Metric | Value |
| --- | --- |
| Capex estimate (P50) | EUR 78.0 m |
| Open risks | 17 |
| Consultation responses to date | 299 |
| Development spend to date | EUR 1.88 m |

Development spend vs budget

# Next month

Submit planning application

Finish breeding bird survey

Answer EPC bidder clarifications