Monthly Status Report – June 2026

Millbrook Solar & Storage

Liam McAllister  ·  03 July 2026  ·  MB-PM-RPT-202606

| Area | RAG | Comment |
| --- | --- | --- |
| Overall | Green | Planning application MDC/2026/0412 was submitted on 18 June with 27 supporting documents. |
| Cost | Green | Development spend EUR 2.21 m of EUR 3.10 m budget (71 %) |
| Schedule | Amber | Planning decision Q1 2027 – on track |
| Stakeholders | Green | Consultations held: 2 of 3 |

# Summary

Planning application MDC/2026/0412 was submitted on 18 June with 27 supporting documents. The breeding bird survey finished on 26 June with 23 skylark territories.

# Key figures

| Metric | Value |
| --- | --- |
| Capex estimate (P50) | EUR 78.0 m |
| Open risks | 17 |
| Consultation responses to date | 299 |
| Development spend to date | EUR 2.21 m |

Development spend vs budget

# Next month

Support validation

Lease variation for skylark plots

Receive EPC bids (10 July)