Monthly Status Report – July 2026

Millbrook Solar & Storage

Liam McAllister  ·  02 August 2026  ·  MB-PM-RPT-202607

| Area | RAG | Comment |
| --- | --- | --- |
| Overall | Amber | The application was validated on 2 July. |
| Cost | Green | Development spend EUR 2.36 m of EUR 3.10 m budget (76 %) |
| Schedule | Amber | Highways holding response – recovery plan in place |
| Stakeholders | Amber | Consultations held: 2 of 3 |

# Summary

The application was validated on 2 July. The Highways Authority issued a holding response asking for more detail on Mill Lane, which moved schedule to amber. Three EPC bids were received.

# Key figures

| Metric | Value |
| --- | --- |
| Capex estimate (P50) | EUR 78.0 m |
| Open risks | 17 |
| Consultation responses to date | 299 |
| Development spend to date | EUR 2.36 m |

Development spend vs budget

# Next month

Swept-path analysis and CTMP Rev 2

EPC bidder interviews 4–5 August

Plan consultation #3