Monthly Status Report – August 2026

Millbrook Solar & Storage

Liam McAllister  ·  02 September 2026  ·  MB-PM-RPT-202608

| Area | RAG | Comment |
| --- | --- | --- |
| Overall | Green | The council consultation closed on 6 August with 143 representations. |
| Cost | Green | Development spend EUR 2.48 m of EUR 3.10 m budget (80 %) |
| Schedule | Amber | Planning decision Q1 2027 – on track |
| Stakeholders | Green | Consultations held: 2 of 3 |

# Summary

The council consultation closed on 6 August with 143 representations. Natural England raised no objection subject to conditions. SunForge EPC Ltd was selected as preferred bidder.

# Key figures

| Metric | Value |
| --- | --- |
| Capex estimate (P50) | EUR 78.0 m |
| Open risks | 16 |
| Consultation responses to date | 299 |
| Development spend to date | EUR 2.48 m |

Development spend vs budget

# Next month

Consultation #3 on 16 September

Preferred bidder letter to SunForge

Outline BSMP to fire service