Event plan

North Sea Energy Summit 2026 · Hamburg · 22–24 September 2026 · Booth B4.210

Noah Fischer  ·  10 September 2026  ·  WE-MC-EVT-2026-01

Owner: Noah Fischer · Core team: Leah Goldberg, Ravi Shah, Henrik Larsen (Business Development), Nina Petrova (Recruiting) · Executive sponsor: Dr. Amara Okafor

# 1. The event

The North Sea Energy Summit 2026 takes place at Hamburg Messe from 22 to 24 September 2026. The organisers expect around 14,000 visitors and 480 exhibitors from the offshore wind, grid, hydrogen and maritime sectors. As a Hamburg company in the middle of building Harrow Bay, this is our home game – and the first time we exhibit with our own stand rather than on a partner booth.

| Item | Detail |
| --- | --- |
| Dates | Tue 22 – Thu 24 September 2026, 09:00–18:00 (Thu until 16:00) |
| Venue | Hamburg Messe, Hall B4 |
| Our booth | B4.210 – island stand, 10 × 8 m (80 m²), aisle 21 |
| Build-up | Sat 19 – Mon 21 September |
| Dismantling | Thu 24 September from 16:30, Fri 25 September |
| Keynote | Dr. Amara Okafor, Main Stage, Tue 22 Sep, 10:30–11:00 |
| Panel | Elena Márquez, 'Delivering offshore wind on time', Stage 2, Wed 23 Sep, 14:00 |
| Reception | Co-hosted networking evening, Wed 23 Sep, 19:00, harbour-side venue |

# 2. Objectives

| Objective | KPI | Target |
| --- | --- | --- |
| Generate business leads (offtakers, suppliers, partners) | Qualified leads scanned | 120 (≥ 20 A-leads) |
| Recruit for Harrow Bay and engineering | Candidate conversations / applications | 60 / 30 |
| Position Weyland as a builder | Keynote audience, media mentions | 700 / 25 |
| Strengthen key relationships | Pre-booked meetings at the booth | 35 |

# 3. Booth concept

The stand follows the Powering the North campaign: light oak, Deep Sea walls, teal accents and a 4.4 m LED wall running the campaign loop and live Harrow Bay progress. At the centre a 1:100 model of the Halden HTS-12 turbine on its monopile (on loan from Halden Turbine Systems, arranged via Lars Henriksen) gives visitors a reason to stop. Two meeting rooms and a lounge for pre-booked meetings; a careers wall with QR codes to open roles.

Rendering of the stand, front view (Messebau Kranz, Rev. B).

# 4. Programme highlights

Keynote – 'From steel to sea: building the North Sea's next decade' (Dr. Amara Okafor)

Panel – Elena Márquez with Halden Turbine Systems, Severn Subsea Cables and NordGrid Transmission

Daily booth talks at 11:30 and 15:30: Harrow Bay construction (Felix Brandt), green hydrogen at Eastholm (Isabel Ferreira), battery storage (Kwame Mensah)

Careers hour Wed 16:00–17:00 with Nina Petrova and Julia Hoffmann

# 5. Budget

Approved budget EUR 185,000 (Marketing budget 2026). Detailed plan and actuals in Event Budget.xlsx.

# 6. Timeline

| Deadline | Task | Owner |
| --- | --- | --- |
| 31 Jan | Exhibitor contract signed | Noah Fischer |
| 15 Mar | Stand builder selected (3 quotes) | Noah Fischer |
| 30 Apr | Keynote slot confirmed | Noah Fischer |
| 15 Jun | Booth design final (Rev. B) | Ravi Shah |
| 30 Jun | Hotels booked | Leah Goldberg |
| 31 Jul | Giveaways ordered | Leah Goldberg |
| 15 Aug | Staffing rota final | Noah Fischer |
| 1 Sep | Graphics print files delivered | Ravi Shah |
| 14 Sep | Keynote rehearsal | Dr. Amara Okafor |
| 2 Oct | Post-event report | Noah Fischer |

# 7. Risks

| Risk | Mitigation |
| --- | --- |
| Questions about the export cable delay (HB-RISK-017) at the booth or on the panel | Holding statement and Q&A briefed to all booth staff |
| Turbine model damaged in transport | Halden ships in its own crate; insurance via exhibition policy |
| Staff pulled away by project work | Back-up names in rota; Elena only on Wednesday |
| Millbrook protest group at the stand | Unlikely in Hamburg – Tom Berger briefed as contact |