Post-event report

North Sea Energy Summit 2026 · 22–24 September 2026 · Booth B4.210

Noah Fischer  ·  01 October 2026  ·  WE-MC-EVT-2026-02

# Summary

Our first own stand at the North Sea Energy Summit 2026 was a clear success. We held 642 conversations at booth B4.210, scanned 142 leads (27 rated A) and ran 38 pre-booked meetings. Dr. Amara Okafor's keynote 'From steel to sea' filled the Main Stage with around 850 people and was quoted in 11 articles. Total cost was EUR 176,000 against a budget of EUR 185,000.

| KPI | Target | Result |  |
| --- | --- | --- | --- |
| Qualified leads | 120 | 142 | ✔ |
| A-leads | 20 | 27 | ✔ |
| Pre-booked meetings | 35 | 38 | ✔ |
| Candidate conversations | 60 | 71 | ✔ |
| Applications (until 1 Oct) | 30 | 24 | ✘ (still coming in) |
| Keynote audience | 700 | ~ 850 | ✔ |
| Media mentions | 25 | 41 | ✔ |
| Cost per lead | EUR 1,540 | EUR 1,239 | ✔ |

# Booth traffic

Conversations per day (lead app + counter tally).

Wednesday was the strongest day thanks to Elena Márquez's panel at 14:00 and the careers hour. The turbine model was the most photographed object on the stand – many visitors came because colleagues had posted it on LinkedIn.

# Leads

The most valuable conversations were with industrial offtakers: three energy-intensive companies want to discuss PPAs from 2029 onwards, and Arcturus Steel raised a possible second tranche. All A-leads have an owner and a follow-up date in the tracker; target is first contact within ten working days.

# Keynote and panel

Dr. Amara Okafor on the Main Stage, 22 September.

The open account of the cable delay as 'lesson 1' was well received – two journalists mentioned the transparency explicitly. The panel 'Delivering offshore wind on time' (Wed 14:00) had 230 attendees.

# Budget

|  | EUR |
| --- | --- |
| Budget | 185,000 |
| Actual (invoices received to 1 Oct) | 176,000 |
| Under budget | 9,000 |

# What we will change next time

Book the stand in the same position (aisle 21) – the location was excellent

One more person on reception on Tuesday morning (queue at 10:00–11:00 after the keynote)

Order 30 % fewer tote bags, twice as many seed paper cards

Second LED loop focused on careers – the careers wall was too small

Lead app training one week earlier; on day 1 about 20 conversations were not scanned

# Recommendation

Exhibit again in 2027 with the same modular stand (re-use saves an estimated EUR 38,000) and apply for a keynote slot early. Decision by the Executive Board in October.