## Slide 1
Inside Harrow Bay
Lunch & Learn · Elena Márquez · 10 September 2026
WEYLAND ENERGY

## Slide 2
The project in numbers
480
MW – 40 × Halden HTS-12
1.62
EUR bn capex
62 km
per export cable
520k
homes powered
WEYLAND ENERGY · Inside Harrow Bay – construction update
2

## Slide 3
Where we are
• First monopile installed on 7 April 2026
• Offshore substation topside installed on 19 August 2026
• Monopile campaign ongoing with MV Sea Atlas – 13 of 40 installed by early September
• Export cable 2: 8-week delivery delay (HB-RISK-017) – cable lay re-sequenced
WEYLAND ENERGY · Inside Harrow Bay – construction update
3

## Slide 4
Protecting marine life
• Bubble curtains during every piling operation
• Marine mammal observers and acoustic monitoring with Marlow Ecology
• Piling paused during seasonal restrictions
WEYLAND ENERGY · Inside Harrow Bay – construction update
4

## Slide 5
What comes next
Milestone | Planned
First turbine installation | 1 March 2027
First power | 30 September 2027
Commercial operation (COD) | 30 June 2028
WEYLAND ENERGY · Inside Harrow Bay – construction update
5

## Slide 6
Questions?
Want to visit Port of Eastholm? Ask Ingrid Solberg.
WEYLAND ENERGY