Logistics Plan – HTS-12 Turbine Components

Harrow Bay Offshore Wind · Aarhus/Esbjerg → Port of Eastholm

Elena Márquez  ·  21 September 2026  ·  HB-LOG-PLN-0002

# 1. Purpose

This plan describes how the components of the 40 Halden HTS-12 turbines for Harrow Bay travel from the Halden factories in Aarhus and Esbjerg to the Port of Eastholm, how they are stored and pre-assembled, and how the logistics interface with the installation campaign starting on 1 March 2027. It is agreed with Halden Turbine Systems (Lars Henriksen) under contract WE-CON-2025-022.

# 2. Components per turbine set

| Component | Qty | Dimensions | Weight (t) | Origin |
| --- | --- | --- | --- | --- |
| Nacelle incl. hub | 1 | 22 × 10 × 11 m | 520 | Aarhus |
| Blades | 3 | 115 m | 54 each | Esbjerg |
| Tower sections | 4 | Ø 7.0 m, 26–34 m | 95–180 | Aarhus (sub-supplier) |
| Transformer / converter module | 1 | in tower base | 48 | Aarhus |
| Bolts and small parts | 2 containers | 20 ft | 14 | Aarhus |

# 3. Transport

Sea transport on two dedicated feeder vessels (roll-on/lift-off), each carrying 2 complete turbine sets

Delivery term DAP Port of Eastholm, Quay 3 (Incoterms 2020) – risk passes on unloading

Transit time Aarhus – Eastholm: 2.5 days; weather limit for loading Beaufort 6

Marine warranty surveyor approval of sea-fastening for every voyage

# 4. Delivery schedule

Figure 1 – Planned deliveries and installation of turbine sets 2027

Deliveries start in January 2027 to build a buffer of six sets before the first installation on 1 March 2027. The buffer is limited by the storage capacity on Quay 3 (eight sets) and is kept at four to six sets during the campaign.

# 5. Storage and pre-assembly at Port of Eastholm

| Area | Use | Capacity |
| --- | --- | --- |
| Quay 3 – Area C | Tower pre-assembly (2 sections stacked) | 8 sets |
| Quay 2 – Area A | Blade racks (from Feb 2027, after monopiles) | 30 blades |
| Quay 3 – load-out berth | Installation vessel loading | 4 sets per trip |

Spare parts warehouse Quay 3 – handed over in September 2026

# 6. Interfaces and risks

Monopile campaign must free Quay 2 Area A by 31 January 2027 (see HB-RISK-013 and HB-RISK-029)

1,350 t crawler crane reserved under framework FA-2026-01 from 11 January 2027

Customs: components from Denmark to the UK require customs clearance – Halden as exporter, Weyland UK project company as importer of record; duty relief under the UK Global Tariff for wind turbine parts confirmed

Severn export cable 2 delay (HB-RISK-017) does not affect turbine logistics