Tender Evaluation Report – Millbrook EPC

Tender MB-EPC-01 · recommendation for preferred bidder

Elena Márquez  ·  04 September 2026  ·  WE-PRC-TER-2026-04

# 1. Summary and recommendation

Four bids were received on 10 June 2026 for the EPC contract of Millbrook Solar & Storage (85 MWp solar on single-axis trackers with ~ 158,000 bifacial modules and a 20 MW / 40 MWh battery storage system). After technical and commercial evaluation, the evaluation team recommends SunForge EPC Ltd as preferred bidder with a weighted score of 4.46 out of 5 (89%).

Contract award is conditional on planning consent for application MDC/2026/0412 (decision expected Q1 2027). Until then SunForge is engaged under a preferred-bidder letter with an early-works cap of EUR 250,000.

# 2. Results

| Bidder | Price (EUR m) | Weighted score | Rank |
| --- | --- | --- | --- |
| SunForge EPC Ltd | 63.8 | 4.46 | 1 |
| Helios Build Partners | 67.2 | 4.17 | 2 |
| GreenGrid Construction Ltd | 61.9 | 3.92 | 3 |
| Albion Solar Contracting | 59.4 | 3.75 | 4 |

# 3. Key differentiators

SunForge EPC Ltd – strongest yield model (P50 89.4 GWh/a), proven BESS integrator, best biodiversity plan (skylark plots, hedgerow planting). Price 7 % above lowest bid.

GreenGrid Construction – competitive price, but BESS from an unqualified sub-supplier and weak glare assessment for nearby homes.

Helios Build Partners – very good HSE record, highest price, longer programme (14 months).

Albion Solar Contracting – lowest price, but significant technical exclusions (grid connection works, BESS commissioning) that would add an estimated EUR 4.5 m.

# 4. Open points for negotiation

Construction traffic routing to avoid Mill Lane during school hours

Module supply chain traceability (polysilicon origin) – evidence required before award

Price validity extension to 30 June 2027

Liquidated damages for delay: EUR 25,000 per day proposed