IC Paper – Glenmore Onshore Wind Acquisition

Request: approval to submit a binding offer

Jonas Richter  ·  24 July 2026  ·  IC-2026-011

# 1. Decision requested

Approve submission of a binding offer for 100 % of the shares in Glenmore Wind Ltd (48 MW consented onshore wind project, PL-005) at a price of up to EUR 17.6 m, subject to the conditions in section 5.

# 2. Rationale

Consented project – removes 3–4 years of planning risk.

Fits our Scottish operations hub around Kestrel Ridge (shared O&M, spares).

Grid connection offer already in place (Q4 2029).

# 3. Technical due diligence

Engineering's TDD (WE-ENG-RPT-0031) identified two red flags: the vendor's energy yield is overstated (our P50: 147 GWh/a vs. vendor 158 GWh/a) and the grid connection date depends on an uncertain reinforcement. Five amber items can be managed in development.

# 4. Valuation

| Case | P50 (GWh/a) | Equity value (EUR m) |
| --- | --- | --- |
| Vendor case | 158 | 21.0 |
| Weyland base | 147 | 17.6 |
| Grid delay to 2031 | 147 | 14.2 |

# 5. Conditions

Condition precedent: transmission owner confirms reinforcement programme before completion.

Deferred consideration of EUR 2.0 m payable only if the connection date of Q4 2029 is held.

Seller warranties on consent conditions and land rights.

Decision (IC 29 July 2026): approved with a cap of EUR 17.6 m including deferred consideration.