## Timeline
# | Task | Owner | Start | End | Status | Comment
1 | Kick-off meeting | Jonas Richter | 2025-11-20 | 2025-11-20 | Done
2 | Layout and design briefing | Noah Fischer | 2025-11-27 | 2025-12-05 | Done | Layout in-house by Ravi Shah
3 | Photo shoot Kestrel Ridge and Hamburg HQ | Noah Fischer | 2025-12-08 | 2026-01-16 | Done | Snow at Kestrel Ridge – second date 16 Jan
4 | Chapter drafts round 1 | Chapter owners | 2026-01-05 | 2026-01-30 | Done | Operations late (Kestrel T-07 incident)
5 | Preliminary financial figures | Marcus Bell | 2026-01-23 | 2026-02-06 | Done
6 | CEO letter draft | Noah Fischer / Dr. Amara Okafor | 2026-01-26 | 2026-02-20 | Done | Updated after FID
7 | Layout proof round 1 | Ravi Shah | 2026-02-16 | 2026-02-27 | Done
8 | Review round 1 (Executive Board, Legal) | Jonas Richter | 2026-02-27 | 2026-03-05 | Open
9 | Audited figures and auditor's report | Keller & Rowe | 2026-02-02 | 2026-03-17 | Open
10 | Layout proof round 2 | Ravi Shah | 2026-03-06 | 2026-03-13 | Open
11 | Consistency check by auditor | Keller & Rowe | 2026-03-13 | 2026-03-18 | Open
12 | Approval Supervisory Board | Dr. Karin Albrecht | 2026-03-19 | 2026-03-19 | Open
13 | Final PDF, accessibility check | Ravi Shah | 2026-03-20 | 2026-03-24 | Open
14 | Print run (350 copies, recycled paper) | Noah Fischer | 2026-03-23 | 2026-03-31 | Open
15 | Publication, press release, website | Noah Fischer | 2026-03-26 | 2026-03-26 | Open