Harrow Bay Offshore Wind – Final Investment Decision

Board paper for the extraordinary meeting of the Supervisory Board, 12 February 2026

Dr. Amara Okafor  ·  22 January 2026  ·  WE-SB-2026-02-FID

# 1. Decision requested

The Executive Board requests the Supervisory Board to approve the final investment decision (FID) for Harrow Bay Offshore Wind (480 MW) with a total capital expenditure budget of EUR 1,620 m, the execution of the finance documents for EUR 1,100 m senior debt arranged by Hanseatic Infrastructure Bank, and a capital increase of EUR 140 m. Financial close is planned for the same day, 12 February 2026.

# 2. The project

| Item | Value |
| --- | --- |
| Location | UK North Sea, 38 km off the coast of Harrow Bay |
| Capacity | 480 MW |
| Turbines | 40 × Halden HTS-12 (12 MW), rotor diameter 236 m, hub height 140 m |
| Foundations | Monopiles, 9.5 m diameter, water depth 28–36 m |
| Grid connection | 2 × 220 kV export cables, 62 km each, to onshore substation Harrow Bay East |
| Expected generation | 1.9 TWh per year (P50), equivalent to 520,000 homes |
| Development consent | Granted 20 November 2023 |
| Construction start | April 2026 (first monopile) |
| Commercial operation (COD) | 30 June 2028 |

# 3. Capital expenditure

| Package | EUR m |
| --- | --- |
| Wind turbines – Halden Turbine Systems (WE-CON-2025-022) | 575 |
| Monopiles and transition pieces – Rhenus Steelworks (WE-CON-2025-027) | 268 |
| Export and array cables – Severn Subsea Cables (WE-CON-2025-031) | 232 |
| Offshore substation HB-OSS – Norfab Offshore Structures (WE-CON-2025-035) | 196 |
| Marine installation, MV Sea Atlas charter (WE-CON-2025-040), port and logistics | 122 |
| Onshore substation Harrow Bay East and grid works (WE-CON-2025-044) | 61 |
| Development, owner's costs, project management and insurance | 111 |
| Contingency (3.5 % of base capex) | 55 |
| Total capex | 1,620 |

Capex budget at FID, nominal, including contingency

Around 87 % of the base capex is fixed under signed EPCI-type supply and installation contracts. The remaining exposure relates to vessel weather downtime, onshore civil works and owner's costs. The contingency of EUR 55 m was sized with a Monte Carlo analysis at P80; a further EUR 45 m of standby equity is committed by the shareholders.

# 4. Financing

# 4. Financing

Term sheet agreed with Hanseatic Infrastructure Bank; syndicate of five lenders, credit approvals expected early February. Pricing and hedging to be finalised.

# 5. Returns

Equity IRR of 10.1 % (P50) based on the December model; to be updated.