Harrow Bay Offshore Wind – Final Investment Decision

Board paper for the extraordinary meeting of the Supervisory Board, 12 February 2026

Jonas Richter  ·  03 February 2026  ·  WE-SB-2026-02-FID

# 1. Decision requested

The Executive Board requests the Supervisory Board to approve the final investment decision (FID) for Harrow Bay Offshore Wind (480 MW) with a total capital expenditure budget of EUR 1,620 m, the execution of the finance documents for EUR 1,100 m senior debt arranged by Hanseatic Infrastructure Bank, and a capital increase of EUR 140 m. Financial close is planned for the same day, 12 February 2026.

# 2. The project

| Item | Value |
| --- | --- |
| Location | UK North Sea, 38 km off the coast of Harrow Bay |
| Capacity | 480 MW |
| Turbines | 40 × Halden HTS-12 (12 MW), rotor diameter 236 m, hub height 140 m |
| Foundations | Monopiles, 9.5 m diameter, water depth 28–36 m |
| Grid connection | 2 × 220 kV export cables, 62 km each, to onshore substation Harrow Bay East |
| Expected generation | 1.9 TWh per year (P50), equivalent to 520,000 homes |
| Development consent | Granted 20 November 2023 |
| Construction start | April 2026 (first monopile) |
| Commercial operation (COD) | 30 June 2028 |

# 3. Capital expenditure

| Package | EUR m |
| --- | --- |
| Wind turbines – Halden Turbine Systems (WE-CON-2025-022) | 575 |
| Monopiles and transition pieces – Rhenus Steelworks (WE-CON-2025-027) | 268 |
| Export and array cables – Severn Subsea Cables (WE-CON-2025-031) | 232 |
| Offshore substation HB-OSS – Norfab Offshore Structures (WE-CON-2025-035) | 196 |
| Marine installation, MV Sea Atlas charter (WE-CON-2025-040), port and logistics | 122 |
| Onshore substation Harrow Bay East and grid works (WE-CON-2025-044) | 61 |
| Development, owner's costs, project management and insurance | 111 |
| Contingency (3.5 % of base capex) | 55 |
| Total capex | 1,620 |

Capex budget at FID, nominal, including contingency

Around 87 % of the base capex is fixed under signed EPCI-type supply and installation contracts. The remaining exposure relates to vessel weather downtime, onshore civil works and owner's costs. The contingency of EUR 55 m was sized with a Monte Carlo analysis at P80; a further EUR 45 m of standby equity is committed by the shareholders.

# 4. Financing

| Lender | Role | EUR m |
| --- | --- | --- |
| Hanseatic Infrastructure Bank | Mandated lead arranger, facility and security agent | 350 |
| Nordvik Export Finance (ECA-covered tranche) | Lender | 300 |
| Elbe Commercial Bank | Lender | 200 |
| Caledonia Capital Bank plc | Lender | 150 |
| Lindwurm Infrastructure Debt Fund II | Institutional lender | 100 |
| Total senior debt |  | 1,100 |

Facility: EUR 1,100 m senior secured construction and term loan facility

Financial close: 12 February 2026

Tenor: Construction period plus 18 years after COD (final maturity 2046)

Margin: 165 bps during construction, 150–190 bps step-up during operations

Interest hedging: 85 % of the expected debt hedged with amortising swaps at 2.74 % (5 counterparties)

Debt : equity: 68 : 32 (EUR 1,100 m debt / EUR 520 m equity)

Equity first: Yes – equity of EUR 520 m fully contributed before first debt drawdown

DSCR covenant: Lock-up 1.15x, default 1.05x (historic and projected, P90)

Sizing DSCR: 1.30x P90 / 1.40x P50

Contingency: EUR 96 m contingency in the budget plus EUR 45 m standby equity

Revenue support: 15-year PPA WE-PPA-2026-004 with Arcturus Steel AG for 150 MW plus CfD for the remaining capacity

Lenders' technical adviser: Strandberg Technical Advisory

# 5. Returns

| Metric | P50 | P90 |
| --- | --- | --- |
| Project IRR (post-tax, nominal) | 7.6 % | 6.4 % |
| Equity IRR (post-tax, nominal) | 10.4 % | 8.1 % |
| Minimum DSCR | 1.40x | 1.30x |
| Payback (from COD) | 11.2 years | 13.5 years |
| Levelised cost of energy | EUR 71 / MWh | EUR 79 / MWh |

The equity IRR exceeds the hurdle rate of 9.0 % for contracted offshore wind set in the investment policy. Around 42 % of the P50 output is sold under the 15-year PPA with Arcturus Steel AG, which is expected to be signed in the first half of 2026; the remainder benefits from a contract for difference. A 20 % decline of merchant prices in the post-CfD tail reduces the equity IRR by 0.7 percentage points.

# 6. Key risks

| Risk | Mitigation | Rating |
| --- | --- | --- |
| Supply chain – export cable manufacturing | Factory acceptance tests witnessed by owner's engineer; delay LDs under WE-CON-2025-031; 14 weeks float to COD | Medium |
| Weather downtime during installation | P75 weather allowance in schedule; MV Sea Atlas charter with extension option | Medium |
| Marine mammals and seabirds | Bubble curtains, seasonal piling restrictions, monitoring by Marlow Ecology | Low |
| Interest rates | 85 % hedged at 2.74 % at financial close | Low |
| Grid connection by NordGrid Transmission | Connection agreement signed; onshore works started 2025 | Low |

# 7. Conditions precedent

Credit approvals of all five lenders (received 3 February 2026)

Lenders' technical adviser Strandberg Technical Advisory – final report without material findings

Model audit by Keller & Rowe – clean opinion

Insurance programme placed (construction all risks, delay in start-up)

Capital increase of EUR 140 m subscribed