## Register
Permit ID | Project | Permit / consent | Authority | Reference | Granted | Expiry | Status | Owner | Next review
PRM-001 | Harrow Bay | Development Consent Order | Secretary of State (Energy) | HB-DCO-2023 | 2023-11-20 | — | Granted | Charlotte Dubois | 2026-11-02
PRM-002 | Harrow Bay | Marine licence – generation assets | Marine licensing authority | ML/2023/00417 | 2023-11-20 | 2033-11-19 | Granted | Charlotte Dubois | 2026-11-02
PRM-003 | Harrow Bay | Marine licence – transmission assets | Marine licensing authority | ML/2023/00418 | 2023-11-20 | 2033-11-19 | Granted | Charlotte Dubois | 2026-12-01
PRM-004 | Harrow Bay | European protected species licence (porpoise) | Nature conservation body | EPS-2026-0112 | 2026-03-18 | 2027-03-17 | Granted | Ahmed Rahimi | 2026-11-02
PRM-005 | Harrow Bay | Onshore substation building control | Harrow Bay District Council | BC/2025/1188 | 2025-08-14 | — | Granted | Ahmed Rahimi | 2026-10-15
PRM-006 | Harrow Bay | Port of Eastholm works licence | Port of Eastholm | PE-WL-2026-07 | 2026-01-20 | 2028-12-31 | Granted | Ahmed Rahimi | 2026-10-15
PRM-007 | Harrow Bay | Traffic regulation order – landfall | County Highways | TRO-2026-031 | 2026-05-02 | 2026-12-31 | Granted | Ahmed Rahimi | 2027-01-15
PRM-008 | Harrow Bay | Abnormal loads notifications (transformers) | County Highways | AIL-2026-14 | 2026-02-10 | 2026-12-31 | Granted | Charlotte Dubois | 2026-10-15
PRM-009 | Harrow Bay | Waste carrier registration | Environment regulator | CBDU-HB-2026 | 2026-02-01 | 2029-01-31 | Granted | Ahmed Rahimi | 2026-10-15
PRM-010 | Harrow Bay | Discharge consent – onshore substation drainage | Environment regulator | DC-2026-0217 | 2026-04-22 | — | Granted | Ahmed Rahimi | 2026-11-02
PRM-011 | Kestrel Ridge | Planning consent (wind farm, 18 turbines) | Scottish Borders planning authority | KR/19/00782/FUL | 2020-06-11 | 2049-03-14 | Granted | Charlotte Dubois | 2026-12-01
PRM-012 | Kestrel Ridge | Aviation lighting consent | Aviation authority | AV-KR-2023-09 | 2023-04-03 | — | Granted | Charlotte Dubois | 2027-01-15
PRM-013 | Kestrel Ridge | Water abstraction (welfare) | Environment regulator | CAR/R/1188842 | 2023-09-01 | 2028-08-31 | Granted | Ahmed Rahimi | 2026-10-15
PRM-014 | Kestrel Ridge | Waste management exemption | Environment regulator | WME-KR-2024 | 2024-02-01 | 2027-01-31 | Granted | Ahmed Rahimi | 2027-01-15
PRM-015 | Kestrel Ridge | Crane permit – T-07 gearbox exchange | Scottish Borders roads | RP-2026-0041 | 2026-01-26 | 2026-02-20 | Expired | Charlotte Dubois | 2027-01-15
PRM-016 | Kestrel Ridge | Generation licence exemption confirmation | Energy regulator | EXM-KR-2023 | 2023-12-01 | — | Granted | Charlotte Dubois | 2026-11-02