## Risk assessment
# | Activity | Hazard | Who may be harmed | S | L | Risk | Controls | S (res.) | L (res.) | Residual risk | Owner
2 | Monopile upending | Load failure / sling break | Deck crew, crane operator | 5 | 2 |  | Certified rigging, lift plan, exclusion zone | 5 | 1 |  | Atlas Marine
3 | Piling | Noise exposure > 85 dB(A) | All on deck | 3 | 4 |  | Hearing protection zones, noise survey | 3 | 2 |  | Atlas Marine
4 | Piling | Underwater noise – harbour porpoise | Marine mammals | 4 | 3 |  | Bubble curtain, soft start, MMO + PAM, 30 min pre-watch | 4 | 1 |  | Clara Neumann
5 | Jacking operations | Punch-through of jack-up leg | All on board | 5 | 2 |  | Site-specific geotechnical assessment, preloading | 5 | 1 |  | Atlas Marine / Oliver Grant
6 | Personnel transfer | Fall into water during gangway / CTV transfer | Technicians | 5 | 2 |  | Sea state limits, lifejackets, MOB boat, PLBs | 5 | 1 |  | Ingrid Solberg
7 | Work on transition piece | Fall from height | Technicians | 5 | 2 |  | Harness, twin lanyard, rescue plan, GWO | 5 | 1 |  | Atlas Marine
8 | Grouting / bolting | Hand injury in bolt tensioning tools | Technicians | 3 | 3 |  | Hand-free tools, training, gloves | 3 | 2 |  | Atlas Marine
9 | Night work | Fatigue | All crew | 4 | 3 |  | Rota max. 21 days, fatigue checks, rest hours | 4 | 2 |  | Felix Brandt
10 | Weather | Lifting in high wind | Deck crew | 4 | 3 |  | Wind limits, met forecasts, stop-work | 4 | 1 |  | Atlas Marine
11 | Hydraulic systems | Oil spill to sea | Environment | 3 | 3 |  | Drip trays, spill kits, SOPEP | 3 | 2 |  | Atlas Marine
12 | Medical | Serious injury / illness far offshore | All on board | 5 | 2 |  | Offshore medic, helicopter medevac procedure, ERP | 4 | 2 |  | Hannah Weber