## Plan
WBS | Workstream / task | Owner | Start | End | Status | % complete | Dependency | Comment
1 | Programme set-up | Katarzyna Nowak | 2025-06-02 | 2025-08-29 | Done | 100% |  | Board mandate 2025-05-27
1.1 | ISMS scope and context (clauses 4.1–4.3) | Katarzyna Nowak | 2025-06-02 | 2025-07-31 | Done | 100% |  | Scope statement approved
1.2 | Information security policy (5.2) | Katarzyna Nowak | 2025-06-16 | 2025-08-29 | Done | 100% | 1.1 | Re-approved 2026-06-30
2 | Risk management | Katarzyna Nowak | 2025-09-01 | 2026-03-31 | Done | 100% | 1
2.1 | Asset inventory incl. OT (5.9) | Jan Kowalski | 2025-09-01 | 2025-12-19 | Done | 100% |  | ~ 1,150 assets
2.2 | Risk assessment workshops (8 departments + OT) | Katarzyna Nowak | 2025-10-06 | 2026-01-30 | Done | 100% | 2.1 | 64 risks identified
2.3 | Risk treatment plan and SoA v1 | Katarzyna Nowak | 2026-02-02 | 2026-03-31 | Done | 100% | 2.2
3 | Control implementation | Katarzyna Nowak | 2026-01-12 | 2026-12-18 | In progress | 68% | 2

## Milestones
Milestone | Planned | Forecast | Status
Board mandate | 2025-05-27 | 2025-05-27 | Done
Scope and policy approved | 2025-08-29 | 2025-08-29 | Done
Risk assessment completed | 2026-01-30 | 2026-01-30 | Done
SoA v1 approved | 2026-03-31 | 2026-03-27 | Done
MFA 100 % | 2026-04-30 | 2026-04-22 | Done
OT segregation Kestrel Ridge | 2026-10-30 | 2026-11-27 | Delayed (firewall delivery)
File services on OpenCloud (all departments) | 2026-12-18 | 2026-12-18 | On track
Internal audit completed | 2027-01-29 | 2027-01-29 | On track
Management review | 2027-02-26 | 2027-02-26 | On track
Stage 1 audit | 2027-03-19 | 2027-03-19 | On track
Stage 2 audit | 2027-05-21 | 2027-05-21 | On track
ISO 27001 certificate | 2027-06-30 | 2027-06-30 | On track