## Plan
WBS | Workstream / task | Owner | Start | End | Status | % complete | Dependency | Comment
1 | Programme set-up | Katarzyna Nowak | 2025-06-02 | 2025-08-29 | Done | 100% |  | Board mandate 2025-05-27
1.1 | ISMS scope and context (clauses 4.1–4.3) | Katarzyna Nowak | 2025-06-02 | 2025-07-31 | Done | 100% |  | Scope statement approved
1.2 | Information security policy (5.2) | Katarzyna Nowak | 2025-06-16 | 2025-08-29 | Done | 100% | 1.1 | Re-approved 2026-06-30
2 | Risk management | Katarzyna Nowak | 2025-09-01 | 2026-03-31 | Done | 100% | 1
2.1 | Asset inventory incl. OT (5.9) | Jan Kowalski | 2025-09-01 | 2025-12-19 | Done | 100% |  | ~ 1,150 assets
2.2 | Risk assessment workshops (8 departments + OT) | Katarzyna Nowak | 2025-10-06 | 2026-01-30 | Done | 100% | 2.1 | 64 risks identified
2.3 | Risk treatment plan and SoA v1 | Katarzyna Nowak | 2026-02-02 | 2026-03-31 | Done | 100% | 2.2
3 | Control implementation | Katarzyna Nowak | 2026-01-12 | 2026-12-18 | In progress | 48% | 2
3.1 | MFA for all accounts incl. guests (8.5) | Jan Kowalski | 2026-01-12 | 2026-04-30 | Done | 100% |  | 100 % since 2026-04-22
3.2 | Privileged access management (8.2) | Northlight IT Services | 2026-03-02 | 2026-09-30 | Done | 100% |  | Tiered admin accounts
3.3 | Backup & recovery concept and restore tests (8.13) | Jan Kowalski | 2026-02-16 | 2026-07-31 | Done | 100% |  | Quarterly tests
3.4 | OT network segregation Kestrel Ridge (8.22) | Jan Kowalski / Sara Lindgren | 2026-04-06 | 2026-11-27 | In progress | 42% |  | Firewall delivered
3.5 | Supplier security (5.19–5.22) | Katarzyna Nowak / Priya Nair | 2026-03-02 | 2026-10-30 | In progress | 52% |  | Questionnaires to 24 critical suppliers
3.6 | Secure file sharing – migration to OpenCloud (5.14, 5.23) | Katarzyna Nowak | 2026-06-01 | 2027-03-31 | In progress | 24% |  | See migration project plan
3.7 | Logging and monitoring with MSP SOC (8.15, 8.16) | Northlight IT Services | 2026-05-04 | 2026-11-30 | In progress | 39%
3.8 | Business continuity – ICT readiness (5.29, 5.30) | Katarzyna Nowak | 2026-07-01 | 2026-12-18 | In progress | 21% | 3.3 | BIA done
4 | Awareness and training (6.3) | Katarzyna Nowak | 2026-01-12 | 2027-03-31 | In progress | 49%
4.1 | Phishing simulations (quarterly) | Katarzyna Nowak | 2026-02-01 | 2026-12-15 | In progress | 52% |  | Report rate 61 % in Sep
4.2 | E-learning SEC-01/SEC-02 for all staff | Julia Hoffmann | 2026-01-12 | 2026-12-31 | In progress | 64% |  | 91 % completion
5 | Documentation and evidence | Katarzyna Nowak | 2026-03-02 | 2027-02-26 | In progress | 32%
6 | Internal audit and management review | Katarzyna Nowak | 2026-11-02 | 2027-02-26 | Planned | 0% | 3, 5
6.1 | Internal audit (external auditor support) | Ostwald Audit Partners | 2026-11-16 | 2027-01-29 | Planned | 0%
6.2 | Management review (9.3) | Executive Board | 2027-02-15 | 2027-02-26 | Planned | 0% | 6.1
7 | Certification | Katarzyna Nowak | 2027-03-01 | 2027-06-30 | Planned | 0% | 6 | Target Q2 2027
7.1 | Stage 1 audit (documentation) | Certification body | 2027-03-15 | 2027-03-19 | Planned | 0% | 6.2 | Body selected: NordCert GmbH
7.2 | Stage 2 audit (implementation) | Certification body | 2027-05-10 | 2027-05-21 | Planned | 0% | 7.1
7.3 | Certificate issued | Certification body | 2027-06-30 | 2027-06-30 | Planned | 0% | 7.2 | Milestone

## Milestones
Milestone | Planned | Forecast | Status
Board mandate | 2025-05-27 | 2025-05-27 | Done
Scope and policy approved | 2025-08-29 | 2025-08-29 | Done
Risk assessment completed | 2026-01-30 | 2026-01-30 | Done
SoA v1 approved | 2026-03-31 | 2026-03-27 | Done
MFA 100 % | 2026-04-30 | 2026-04-22 | Done
OT segregation Kestrel Ridge | 2026-10-30 | 2026-11-27 | Delayed (firewall delivery)
File services on OpenCloud (all departments) | 2026-12-18 | 2026-12-18 | On track
Internal audit completed | 2027-01-29 | 2027-01-29 | On track
Management review | 2027-02-26 | 2027-02-26 | On track
Stage 1 audit | 2027-03-19 | 2027-03-19 | On track
Stage 2 audit | 2027-05-21 | 2027-05-21 | On track
ISO 27001 certificate | 2027-06-30 | 2027-06-30 | On track

## Budget
Cost item | 2025 (EUR) | 2026 (EUR) | 2027 (EUR) | Total
External consultancy (gap analysis, risk method) | 38000 | 24000 | 8000
Northlight SOC / logging service | 0 | 42000 | 84000
OT firewall and switches Kestrel Ridge | 0 | 61000 | 0
File services platform (subscription + hosting) | 0 | 38000 | 96000
Awareness platform and phishing simulations | 6500 | 14000 | 14000
Internal audit support | 0 | 9000 | 12000
Certification audit (stage 1 + 2) | 0 | 0 | 27500
Total