File Services Migration to OpenCloud

Project plan – sovereign file sync & share for all spaces

Katarzyna Nowak  ·  10 September 2026  ·  IT-PRJ-2026-03

# 1. Why we are doing this

Weyland's documents live in three places today: Windows file servers in Hamburg and Edinburgh (about 9.6 TB, 2.1 million files), personal OneDrive folders, and a US-hosted file sharing service that 87 colleagues use to exchange files with partners such as Halden Turbine Systems and Marlow Ecology. The result: duplicate versions, links that never expire, no central overview of what is shared with whom – and project data from a critical infrastructure operator stored outside the EU.

We will replace this with one file sync & share platform for all spaces, based on OpenCloud, an open-source platform, self-hosted in the EU data centres of our MSP Northlight IT Services (Frankfurt / Nuremberg).

# 2. Goals

| Goal | Measure of success |
| --- | --- |
| Digital sovereignty | 100 % of business documents stored in EU data centres under our control; no proprietary lock-in (open standards, ODF) |
| Secure partner collaboration | All external sharing via guest accounts or federated shares with expiry; legacy SaaS switched off by 31 Jan 2027 |
| One structure | Spaces for every department and project, with managers, editors and viewers – mirrors the organisation |
| Find things | Full-text search across all spaces the user may access |
| ISO 27001 | Evidence for controls 5.14 information transfer, 5.23 cloud services, 8.13 backup |
| Cost | Licence and hosting cost ≤ EUR 150k p.a., lower than today's file servers + SaaS (EUR 182k p.a.) |

# 3. Scope

25 spaces: 6 project spaces (Harrow Bay, Millbrook, Kestrel Ridge, Fenwick, Pipeline, Hydrogen), 14 department spaces, 5 cross-functional spaces (Company Handbook, Brand Assets, Annual Report, Sustainability Report, Onboarding & Learning)

Personal folders for all 450 employees (replacing home drives)

~ 60 guest users from partners; federated sharing with partners that run compatible platforms

Out of scope: SCADA historian data, ERP attachments, email archives

# 4. Wave plan

| Wave | Spaces | Users | Go-live | Status |
| --- | --- | --- | --- | --- |
| Pilot | IT & Security, HR & People, Company Handbook | 38 | 2026-09-07 | Done – feedback 4.4/5 |
| Wave 1 | Finance, Legal, Marketing, Engineering, Brand Assets, Onboarding & Learning | ~ 140 | 2026-11-09 | Preparation |
| Wave 2 | Harrow Bay, Millbrook, Kestrel Ridge, Fenwick, Hydrogen, Procurement, Grid & Permits, HSE | ~ 260 + 60 guests | 2027-01-18 | Planning; Harrow Bay after Legal sign-off (litigation hold) |
| Wave 3 | Executive Board, Investor Relations, Pipeline, archive data | ~ 30 | 2027-03-01 | Planning |
| Decommissioning | File servers FS01–FS04, legacy SaaS | – | 2027-03-31 | – |

# 5. Approach

Clean-up before move: space managers decide what moves; files untouched for > 5 years go to the archive space (read-only).

Keep history where it matters: version history is migrated for controlled documents and all files under legal hold.

Permissions by space, not by folder: we flatten the old folder ACLs (> 4,000 unique permissions) into space roles.

Training: 30-minute sessions per department, Lunch & Learn on 5 November 2026, quick guide in the Company Handbook.

Freeze: legacy shares become read-only one week after each wave.

# 6. Risks

| Risk | Mitigation |
| --- | --- |
| Users keep working on old shares | Read-only switch after each wave; redirects in mapped drives |
| Broken links in Excel models (Finance) | Link scan before wave 1; Finance champions fix models in test space |
| Partner acceptance of new sharing | Early test with Halden (federated share, CHG-2026-140) and Marlow Ecology (guest accounts) |
| Legal hold on Harrow Bay data | Migrate with full version history; hash lists verified by Legal before cut-over |
| Works council concerns about logging | BV-2025-03 Annex 1 updated; activity logs only for security incidents |

# 7. Budget and governance

One-off: EUR 64,000 (Northlight migration services, 40 consulting days, training). Running: EUR 96,000 enterprise support subscription (WE-CON-2026-029, in negotiation) + EUR 52,000 hosting (CR-09) per year. Steering: ISO 27001 steering committee; project lead Katarzyna Nowak; technical lead Jan Kowalski; DPIA-2026-03 by Legal; works council informed 3 August 2026.