Project Execution Plan

Millbrook Solar & Storage

Liam McAllister  ·  20 January 2026  ·  MB-PM-PLN-0001

# 1. Purpose and scope

This Project Execution Plan (PEP) sets out how Weyland Energy will take Millbrook Solar & Storage from planning through to financial close and the start of construction. It covers the 85 MWp ground-mounted solar farm on single-axis trackers, the co-located 20 MW / 40 MWh battery energy storage system (BESS) and the 3.8 km 132 kV cable route to the Millbrook 132 kV substation operated by NordGrid Transmission. The site covers 142 ha of former arable farmland north of Millbrook village.

The PEP is a living document. It is owned by the Project Manager and reviewed at every Project Board. Changes to scope, budget or key dates above the tolerances in section 6 need Project Board approval and, where they affect the investment case, Investment Committee approval.

# 2. Project summary

| Item | Value |
| --- | --- |
| Installed capacity | 85 MWp DC / 68.4 MWac |
| Export limit (connection offer) | 70 MW at Millbrook 132 kV substation |
| Battery storage | 20 MW / 40 MWh battery energy storage system (BESS) |
| Modules | ~ 158,000 bifacial modules on single-axis trackers |
| Expected generation | 91.3 GWh per year (P50), ~ 26,000 homes |
| Site area | 142 ha (leased, 40 years, lease signed 18 Nov 2025) |
| Planning reference | MDC/2026/0412 – submitted 18 June 2026, decision expected Q1 2027 |
| EPC | SunForge EPC Ltd (preferred bidder) |
| Capex budget | EUR 78 m (incl. EUR 4.4 m contingency) |
| Community fund | EUR 120,000 per year for the operating life |

# 3. Organisation

# 4. Key milestones

| Milestone | Date | Status |
| --- | --- | --- |
| Land lease signed | 18 Nov 2025 | Complete |
| Public consultation #1 | 11 Mar 2026 | Planned |
| Public consultation #2 | May 2026 | Planned |
| Planning application submitted | June 2026 | Planned |
| Planning decision | Q4 2026 | Planned |
| Financial close | Q2 2027 | Planned |